## Automation Features PI11&PI12
Role | Feature | Precondition | Progress | Data Driven | Iteration | Estimate | Issue encountered
| Assign Apps From Global To Personal Queue - CreditAgreement |  | 100%
| Assign Apps From Global To Personal Queue - Data Capture |  | 100%
| Assign Apps From Personal To Global |  | 100%
Fax Indexing | Indexing - Form 17.1 | Fresh ID Number | 100% | Yes
| Indexing -Proposal | Same Fresh ID Number - To allow End to End Testing | 100% | Yes
Data Capture | Data Capturing | Same Fresh ID Number - To allow End to End Testing | 100% | No - testing data hard coded
| Modify Application Applicants |  | 0% |  | 12.5 | 8
Edit COB | Edit Credit Agreements |  | 0% |  | 12.5 | 8
Add COB | Add COB |  | 100% | No - testing data hard coded |  |  | For some strange reasons, sometimes when it runs the 1st time not able to select Card
Proposal Credit Risk Assessment | Credit Risk Assessment update and accept proposal |  | 98% | No - testing data hard coded |  |  | Works well within Chrome, but Edge it doesn’t pass a certain screen & fix the issue to be able to send email
| Credit Risk Assessment update and decline proposal |  | 100% | No - testing data hard coded
| Credit Assessment Create Counter Automatically |  | 100% | No - testing data hard coded
| Credit Risk Assessment Decline |  | 100% | No - testing data hard coded
| Credit Risk Assessment assign to risk manager |  | 100% | No - testing data hard coded
| Credit Risk Assessment Counter |  | 100% | No - testing data hard coded
| Edit Credit Risk Assessment Accept |  | 100% | No - testing data hard coded
| Edit Credit Risk Assessment Decline |  | 100% | No - testing data hard coded
| Edit Credit Risk Assessment Update And Accept |  | 100% | No - testing data hard coded
| Edit Credit Risk Assessment Update And Decline |  | 100% | No - testing data hard coded
| Edit Credit Risk Assessment Assign To Risk Manager |  | 100% | No - testing data hard coded
| Edit Credit Risk Assessment Counter |  | 100% | No - testing data hard coded |  |  | 1. On Add Term, investigate why one is not able to enter "TermInterest" and Investigate why sometimes its failing on Capture Proposal especially when running on Edge, when no any browser session opened
| Edit Risk Assessment Create Counter Automatically |  | 100% | No - testing data hard coded |  |  | Investigate why one is not able to enter "Interest" but in Chrome is fine, failing in Edge
| Capture Facilitated Proposal Accept | Developers need to prepare data for us | 100% |  | 12.1 | 16
| Capture Facilitated Proposal Decline | Developers need to prepare data for us | 100% |  | 12.1 | 8
| Capture Facilitated Update and Accept | Developers need to prepare data for us | 100% |  | 12.1 | 16
| Capture Facilitated Update and Decline | Developers need to prepare data for us | 100% |  | 12.1 | 8
| Edit Facilitated Proposal |  | 100% |  | 12.1 | 8
| Capture Referred Rearrangements |  | 100% |  | 12.1 | 16
Proposal Credit Risk Management | Credit Risk Management |  | 0% |  | 12.5 | 16
| Edit Credit Risk Management |  | 0% |  | 12.5 | 8
Proposal Credit Prep | Credit Preparations Voluntary/Proposal Credit Prep | Same Fresh ID Number - To allow End to End Testing | 100% | No - testing data hard coded |  |  | On Add Term, investigate why one is not able to enter "TermInterest" but in Chrome is fine, failing in Edge
| Credit Preparations Application to court |  | 100% | No - testing data hard coded
Proposal Specialized Portfolio | Proposal Specialized Portfolio |  | 0% |  | 12.5 | 16
| Edit Proposal Specialized Portfolio |  | 0% |  | 12.5 | 8
Restructure(1) | Restructure |  | 100% |  | 12.4 | 8
| Arrears Monitoring |  | 100% |  | 12.4 | 8
| Insurance Monitoring |  | 100% |  | 12.4 | 8
Application to Court Proposal Credit Risk Assessment | Application to Court Proposal Credit Risk Assessment |  | 0% |  | 12.5 | 32
| Edit Application to Court Proposal Credit Risk Assessment |  | 0% |  | 12.5 | 16
Application to Court Proposal Credit Risk Management | Application to Court Proposal Credit Risk Management |  | 0% |  | 12.5 | 16
| Edit Application to Court Proposal Management |  | 0% |  | 12.5 | 16
Court Order(3) | Capture Court Order |  | 0% |  | 12.3 | 8
| Edit Court Order |  | 0% |  | 12.3 | 4
Application to Court(2) | Capture application to court |  | 0% |  | 12.4 | 12
| Awaiting court date |  | 0% |  | 12.4 | 4
| Awaiting DC to App to court response |  | 0% |  | 12.4 | 8
| Edit Application to court proposal |  | 0% |  | 12.4 | 8
Legal Review | Document Re-evaluation |  | 0% |  | 12.4 | 8
| Notices |  | 0% |  | 12.2 | 16
| Reckless Lending Attorney Management |  | 0% |  | 12.2 | 16
| Legal review |  | 0% |  | 12.2 | 8
| Update Instructions |  | 0% |  | 12.2 | 16
| Awaiting court outcome |  | 0% |  | 12.2 | 8
| Capture postponement date |  | 0% |  | 12.3 | 4
| Rescission |  | 0% |  | 12.3 | 16
| Capture Rescission Court Outcome |  | 0%
| Update Rescission Instructions |  | 0% |  | 12.3 | 8
| Capture awaiting court date |  | 0% |  | 12.3 | 8
| Capture awaiting postponement date |  | 0% |  | 12.3 | 8
400
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Very difficult because steps are inside functions instead feature file