## 9Sept20 (hidden)
IFTR DSU - 9 September 2020
Reporting Category / Issue | Task | Outstanding task/Progress | Responsibility | Date to complete | Blockers/Escalation | Comments
Bopcus/Non-reportable | Requirements | Not applicable
| Write up (GAML/GL) | Not applicable
| Mapping | TBA - after testing of comments node. TN investigating blank comments | Tlalane |  |  | Items not liked to institutions/swift code - Group AML to provide feedback and could impact mapping
| Development | Not applicable
| Testing | Regression testing for comments node | CIB: Ravi/Lakshmi RBB: Nkateko/Ntsoaki | CIB: COB 9 Sept 20 RBB: TBA | RBB/Wealth testing to be planned and executed | FACTS/MCA comments node. No MCA transactions to be tested. Look at exceptions file to see if MCA (MC) for transaction
| Defect |  |  |  |  | Defects to be listed
Bopcard Resident | Requirements | Not applicable
| Write up (GAML/GL) | Not applicable
| Mapping | Not applicable
| Development | Not applicable
| Testing | In progress | Harry/Tlalane |  |  | Regression testing - Travel Card issue. HY to chat to TL. Meet 9/9 to discuss
Defect
Bopcard Non-resident | Requirements | Not applicable
| Write up (GAML/GL) | Low volumes to Grp AML | Tlalane/Group AML |  |  | Require feedback from Group AML
| Mapping | 1. Reversals: To confirm if the technical solution provided by Gerhard works | Phakamile/Minothi/Melissa |  |  | Mappings updated. Additional accounts to be run through solution (MC). If solution works, mappings will be completed and then developed
|  | 2. Reversals: Mapping updates | Minothi |  |  | Mappings to be updated once testing is done to resolve tech issue
| Development | In progress pending Gideons meetup (Phakaimile, Melissa, Minothi) | Melissa |  |  | On completion of the mappings
| Testing | Test data shared on the 1st Sep | Harry |  |  | Test data provided. HY to start 10/9
Defect
CMA - ACB | Requirements | Not applicable
| Write up (GAML/GL) | Not applicable
| Mapping | Address/city name not in CIS - but need to go to exceptions. |  |  |  | MC/ET investigating as it is free text field Clusters to review data on MDM to resolve address issue
| Development | Reversals completed - interbank issue to be resolved (sequence number issue) | Minothi/Ian/Surekha |  |  | Confirmation required that sequence numbers cannot be amended. Reason field for reversal - if not in file will be not obtained. MC to check mapping and dev. Swift dev to be completed - CIM 900 file
| Testing | In progress | Nkateko |  |  | Location dev completed. Test data to be shared by MC
Defect
CMA - CPS | Requirements | Not applicable
| Write up (GAML/GL) | Not applicable
| Mapping | Address/city name not in CIS - but need to go to exceptions. | Clusters/NDW |  |  | MC/ET investigating as it is free text field Clusters to review data on MDM to resolve address issue
| Development | Not applicable |  |  |  | Swift dev to be completed - CIM 900 file
| Testing | In progress | Ntsoaki |  |  | CPS out in progress (city name issue only issue). Reason field for reversal - if not in file will be not obtained. MC to check mapping and dev
| Defect |  |  |  |  | 2 defects to be addressed (covered under suspense and impersonal accounts)
CMA - Magtape | Requirements | Not applicable
| Write up (GAML/GL) | Not applicable
| Mapping | In progress |  |  |  | MC/ET investigating as it is free text field Clusters to review data on MDM to resolve address issue
| Development | In progress |  |  |  | Swift dev to be completed - CIM 900 file
| Testing | In progress | Harry |  |  | Reason field for reversal - if not in file will be not obtained. MC to check mapping and dev
Defect
Impersonal accounts | Requirements | 1. RBB - List of items to be addressed |  |  |  | Meeting to discuss with Davin on Monday. To discuss items on list
|  | 2. CIB - to check Shantha's examples against latest rules to establish if these transactions will be an issue | Minothi |  |  | MM to request additional fields to check
|  | 3. Wealth - Followed up with Elena as to who will notify GAML of new impersonal accounts | Minothi |  |  | Still to confirm; waitng feedback. LM to escalate
| Write up (GAML/GL) | 1. An addendum to be added once the requirements are finalised | Minothi |  |  | Will be donet when All RBB requirements are complete. Weath to advise notification process to RBB
| Mapping | 1. Mappings to be updated when the requirements are finalised | Minothi
Development
Testing
| Defect | 1. Review of current defect list | Entire team
Suspense accounts | Requirements | 1. CPS, MG and ACB RBB suspense accounts to be investigated to indicate whether they would have underlying clients | Shantha |  |  | Shanta to request assistance from MC - Minothi to be included in meeting
| Write up (GAML/GL) | 1. An addendum to be added once the requirements are finalised | Minothi
Mapping
| Development | Development to take place after finalisation of the mapping update | Melissa
Testing
Defect
CMA Bank Statements | Mappings | 1. Investigate NDW data fields | Phakamile
|  | 2. Update mappings and distribute for sign-off | Minothi
China Systems | Mapping | 1. Engaging with China Systems team to understand transactions | Minothi/Tlalane
| Development | Development for China Systems transactions per mappings | Melissa
| Testing | Regression testing for completed development | TBA
Tracibility matrix | Requirements | 1. Waiting for GAML to load FIC presentations onto sharepoint | GAML
|  | 2. Minothi to work on compiling spreadsheet | Minothi |  |  | GAML to load FIC documents on Sharepoint.
Independent testing | Bopcus |  | Peter
| Non reportable |  | Peter
| Bopcard Resident | In progress | Peter
| Bopcard Non-resident |  | Peter
| CMA - ACB | Completed | Peter
| CMA - CPS | Completed | Peter
| CMA - Magtape | Completed | Peter
ROA exceptions - across all reporting categories | All categories | Resolve whether clients should be included for reporting per the current rule set | Nelene |  |  | Meeting to be held with Alon to discuss issue and resolve way forward (i.e. report clients)
Exceptions management process | All categories | 1. Resolve Finsurv and CMA category financial exceptions process | Nelene |  |  | Finsurv require extract to understand volumes
|  | 2. Resolve cluster client exceptions process | Nelene |  |  | RBB to finalise where exceptions will flow
Country prefix code | All categories | Current proposed solution will not solve for the issue. Clusters to provide alternative solution | Clusters |  |  | Clusters to provide way forward on this. Is this being resolved through the MDM fixes?
Solution design | All categories | IER status - IB to update current document and distribute to Group AML and Group Legal | Ilse |  |  | Ilse to complete write-up on inclusion of IER status for Bopcus
Data lineage | All categories | Confirmation of hand-over to Group AML | Lauretta | Completed |  | Email sent to stakeholders
|  | Analysis hand over to Group AML team | Lauretta | Completed
CIS/MDM migration |  | Testing of exceptions to be completed | Testing team
GATR exceptions automation |  | Development of GATR exceptions process flow | Eric /Adaptris |  | Dependent on completion of exceptions process
Breach process |  | Not at this time | Nelene |  |  | Process has been reviewed and updated. Final review and approval once reporting categories are finalised
Passport/ID no blank |  | Defect to be closed?
FIU message |  | Group AML has escalated to FIC. Awaiting feedback | Group AML | TBA | FIC
Dormant accounts /GL account |  | To be resolved for RBB - escalation to Group AML required | Ilse / Group AML | TBA
Approval of testing by clusters | Testing sign-off by clusters | Complete testing Complete traceability matrix Obtain sign-off | Peter / Testing team
Methodology register | Register of changes required to the methodology | First draft of registrer completed Update as an when required Provide to Group AML for update of methodology document | Lauretta / Group AML
Financial reconciliations | 3 way recon for IFTR | Complete hand-over from James Vlok to Group Finance Complete 3 way recon and obtain approval Implement 3 way recon for IFTR | Lachelle van der Merwe / Group Finance / NDW | TBA |  | GF workshop on Friday 11/9. Have requested weekly update on progress

## 25_Sept_20 (hidden)
IFTR DSU - 02 October 2020
Reporting Category / Issue | Task | Outstanding task/Progress | Responsibility | Date to complete | Blockers/Escalation | Comments
Bopcus/Non-reportable | Requirements | Not applicable
| Write up (GAML/GL) | Not applicable
| Mapping | TBA - after testing of comments node. TN and PZ will investigating the 54 blank comments. | Tlalane and Phakamile |  | Duplicates picked up on on new rules provided | New rules are creating dulicates. Tlalane and Phakimile investigated the Duplicates. The rules work on their side. TN and PZ to sit with MC to discuss today
| Development | Not applicable |  |  |  | Updated
| Testing | Regression testing for comments node | CIB: Ravi/Lakshmi RBB: Nkateko/Ntsoaki | CIB: COB 9 Sept 20 RBB: 25/09 | RBB/Wealth testing to be planned and executed | MCA always in exceptions due to swift, to be tested. Bopcus and Non reportables execution for in and out completed.
| Defect |  |  | 2020-10-09 |  | The same scenario of Debiting the NOSTRO account Crediting the RESCFC I found the transactions under the BOPCUS in . Testing to be finalized end of this week 09/10
Bopcard Resident | Requirements | Not applicable
| Write up (GAML/GL) | Not applicable
| Mapping | Not applicable
| Development | Not applicable
| Testing | In progress | Harry/Tlalane
| Defect |  |  | 2020-10-09 |  | Testing has started, Tester is still finalizing . No issued picked up. Testing to be finalised by EOD
Bopcard Non-resident | Requirements | Not applicable
| Write up (GAML/GL) | Low volumes to Grp AML | Tlalane/Group AML |  |  | Require feedback from Group AML. Deon to review analaysis. LM to follow up with Deon Rheeders.Curency code issue delay the Dev.
| Mapping | 1. Reversals: To confirm if the technical solution provided by Gerhard works | Phakamile/Minothi/Melissa |  |  | Finalising some of the dev leg. Process running and to finalise the exceptions inflow out leg (accurate)
|  | 2. Reversals: Mapping updates | Minothi |  | Req | All mappings done.(Low volumes) Inflow planning session ( linking the country and currency) File requested from Elia teams for investigations
| Development | In progress pending Gideons meetup (Phakaimile, Melissa, Minothi) | Melissa |  |  | Development completed, FIC file sbmission was succesful. Test data to be shared with project team by 28/09
| Testing | Test data shared on the 1st Sep | Harry | 2020-10-09 | Source file | IB to request use of file on layer 0. Email sent to clusters.PM to confirm with Phakamile if she will be extracting the file or a TRS is logged and send to Elias team. PM to follow up
Defect
CMA - ACB | Requirements | Not applicable
| Write up (GAML/GL) | Not applicable
| Mapping | Address/city name not in CIS - but need to go to exceptions. |  |  | Bi | Completed
| Development | Reversals completed - interbank issue to be resolved (sequence number issue) | Minothi/Ian/Surekha | 2020-10-09 | Access still not granted | Reason field for reversal - to be moved to tracking tab. Awaiting the FIC. CIM 900 file - Acess still an issue. Instructions sent to Melissa on how to gain acess.Date formatting issue still persists. We need a remediation process for production. Phakamile to investigate.
| Testing | In progress | Nkateko
Defect
CMA - CPS | Requirements | Not applicable
| Write up (GAML/GL) | Not applicable
| Mapping | Address/city name not in CIS - but need to go to exceptions. | Clusters/NDW |  |  | MC/ET investigating as it is free text field Clusters to review data on MDM to resolve address issue
| Development | Not applicable | NDW | 2020-10-09 | Access still not granted | CIM 900 file - Acess still an issue. Instructions sent to Melissa on how to gain acess.Date formatting issue still persists
| Testing | In progress | Ntsoaki | TBA | address issue dependant on bisyncing issue . Reversals issue dependant on the FIC | CPS out in progress (city name issue only issue). Reason field for reversal -
| Defect |  |  |  |  | 2 defects to be addressed (covered under suspense and impersonal accounts)
CMA - Magtape | Requirements | Not applicable
| Write up (GAML/GL) | Not applicable
| Mapping | In progress |  | TBA |  | MC/ET investigating as it is free text field Clusters to review data on MDM to resolve address issue
| Development | In progress |  | 2020-10-09 |  | CIM 900 file - Acess still an issue. Instructions sent to Melissa on how to gain acess
| Testing | In progress | Harry |  |  | Reason field for reversal issue still persist
Defect
Impersonal accounts | Requirements | 1. RBB - List of items to be addressed |  |  |  | Meeting to discuss with Davin on Monday. To discuss items on list
|  | 2. CIB - to check Shantha's examples against latest rules to establish if these transactions will be an issue | Minothi | 2020-10-12 |  | MM to request additional fields to check
|  | 3. Wealth - Followed up with Elena as to who will notify GAML of new impersonal accounts | Minothi |  |  | Still to confirm; waitng feedback. LM to escalate
| Write up (GAML/GL) | 1. An addendum to be added once the requirements are finalised | Minothi |  |  | Will be donet when All RBB requirements are complete. Weath to advise notification process to RBB
| Mapping | 1. Mappings to be updated when the requirements are finalised | Minothi
Development
Testing
| Defect | 1. Review of current defect list | Entire team
Suspense accounts | Requirements | 1. CPS, MG and ACB RBB suspense accounts to be investigated to indicate whether they would have underlying clients | Shantha |  |  | Shanta to request assistance from MC - Minothi to be included in meeting
| Write up (GAML/GL) | 1. An addendum to be added once the requirements are finalised | Minothi
Mapping
| Development | Development to take place after finalisation of the mapping update | Melissa
Testing
Defect
CMA Bank Statements | Mappings | 1. Investigate NDW data fields | Phakamile |  |  | Code proved to locate fields
|  | 2. Update mappings and distribute for sign-off | Minothi |  |  | MM requested feedback to ET - to request whether it should be incldued or not and then send out for sign-off
China Systems | Mapping | 1. Engaging with China Systems team to understand transactions | Minothi/Tlalane |  |  | Need to obtain underlying client email (LM)
| Development | Development for China Systems transactions per mappings | Melissa
| Testing | Regression testing for completed development | TBA
Tracibility matrix | Requirements | 1. Waiting for GAML to load FIC presentations onto sharepoint | GAML |  |  | GAML to load FIC documents on Sharepoint.
|  | 2. Minothi to work on compiling spreadsheet | Minothi |  |  | GAML to load FIC documents on Sharepoint.
Independent testing | Bopcus |  | Peter
| Non reportable |  | Peter
| Bopcard Resident | In progress | Peter |  |  | PS has few queries, should be compelted by 25/9
| Bopcard Non-resident |  | Peter
| CMA - ACB | Completed | Peter |  |  | N/A
| CMA - CPS | Completed | Peter |  |  | N/A
| CMA - Magtape | Completed | Peter |  |  | N/A
ROA exceptions - across all reporting categories | All categories | Resolve whether clients should be included for reporting per the current rule set | Nelene |  |  | 1. Where the are onboarded will determine inclusion in reporting. 2. Need to ascertain profit centre for exceptions process
Exceptions management process | All categories | 1. Resolve Finsurv and CMA category financial exceptions process | Nelene |  |  | IB to escalate
|  | 2. Resolve cluster client exceptions process | Nelene |  |  | RBB to finalise where exceptions will flow
Country prefix code | All categories | Current proposed solution will not solve for the issue. Clusters to provide alternative solution | Clusters |  |  | Clusters to provide way forward on this. Is this being resolved through the MDM fixes?
Solution design | All categories | IER status - IB to update current document and distribute to Group AML and Group Legal | Ilse |  |  | Ilse to complete write-up on inclusion of IER status for Bopcus
Data lineage | All categories | Confirmation of hand-over to Group AML | Lauretta | Completed |  | Email sent to stakeholders
|  | Analysis hand over to Group AML team | Lauretta | Completed
CIS/MDM migration |  | Testing of exceptions to be completed | Testing team |  |  | Bopcus testing prioritised
GATR exceptions automation |  | Development of GATR exceptions process flow | Eric /Adaptris |  | Dependent on completion of exceptions process
Breach process |  | Not at this time | Nelene |  |  | Process has been reviewed and updated. Final review and approval once reporting categories are finalised
Passport/ID no blank |  | Defect to be closed? |  |  |  | ME team to review whether this is a capturing issue. NS to follow up on this
FIU message |  | Group AML has escalated to FIC. Awaiting feedback | Group AML | TBA | FIC
Dormant accounts /GL account |  | To be resolved for RBB - escalation to Group AML required | Ilse / Group AML | TBA |  | RBB - Need to resolve with Bash on way forward. Finsurv team will deal with exceptions. Shanta to advise whether this could be and issue for CMA transactions
Approval of testing by clusters | Testing sign-off by clusters | Complete testing Complete traceability matrix Obtain sign-off | Peter / Testing team
Methodology register | Register of changes required to the methodology | First draft of registrer completed Update as an when required Provide to Group AML for update of methodology document | Lauretta / Group AML
Financial reconciliations | 3 way recon for IFTR | Complete hand-over from James Vlok to Group Finance Complete 3 way recon and obtain approval Implement 3 way recon for IFTR | Lachelle van der Merwe / Group Finance / NDW | TBA |  | GF workshop on Friday 11/9. Have requested weekly update on progress. IB to follow up on progress
No | Action Items | Responsible | Feedback/Notes | Next follow up date | Status | Defect No
1 | SWIFT Inflow - Lauretta and Tlalane to engage with Mamello on this | LM/TN | 14/9/2020: 1. TN has updated mappings to include IER status and they do have it on BOPCUS for certain transactions. FINSURV team indicated that we need to include IER for BOPCUS. 2. TL and LB to engage with Mamello by COB 16/9 - LM asked to keep this item open till then 22/9/2020: 1. LM has advised that the mappings were updated and that this item should be closed | Thurs, 17th Sep | Closed
2 | SWIFT Outflow - Meeting with Mamello and FINSURV team
2.1 | SWIFT Outflow - Meeting with Mamello and FINSURV team to be held to discuss this | MC | 14/9/2020: 1. Meeting was held on 8/9 to confirm which account numbers the outgoing team would manage 2. Mamello requested dataand indicated that previous extract would suffice but she then requested Aug data - Minothi to confirm with Mamello as whether a new extract is required 16/9/2020: 1. Mamello confirmed that she wants a new extract for August so that it can be distributed to the team for them to advise on the acocunt numbers 2. See 2.3 below | Refer to 2.3 below | Open
2.2. | Meeting on 8/9: Mamello to send an email pertaining to the descriptions she requires on the exception report | Mamello | Mamello has discussed this with Melissa |  | Closed
2.3 | Meeting on 8/9: 2. Melissa to then run an extract for August 2020 to extract the outgoing FINSURV impersonal and suspense account exceptions (this would include all impersonal accounts and not be limited to the list that the incoming team provided) – the following account numbers need to be excluded as they would only be applicable to domestic transactions: 1565000218, 1565000226, 1565000234, 1565000242 The extract to include the descriptions provided by Mamello. | MC | 22/09/2020: 1. Melissa has run the extrat for the data that is available in NDW 2. Mamello has some queries pertaining to the data range as it is not for the 1st Aug - 31st Aug - Melissa has advised that the GPS data is not available in NDW for that date range 3. MC will respond to Mamello's addtional queries. |  | Open
2.4 | Meeting on 8/9: 3. Melissa to distribute the file to Mamello and the project team | MC |  |  | Open
2.5 | Meeting on 8/9: Mamello to send the file to all stakeholders and Dewald to obtain input. The team will also confirm whether we must send all the impersonal account exceptions to them or whether there is a list of accounts that is specific to the outgoing transactions team - this item will also answer Shantha's query about the MFC account number | Mamello |  |  | Open
2.6 | Mtng on 8/9:Minothi to set up meeting with Suzette Steyn and Linda Botman from Cape Town | MM | 22/09/2020: Meeting scheduled for 22/9/2020 with CT stakeholders to discuss exceptions and account numbers that the CT outgoing exceptions team will handle |  | Open
2.7 | Mtng on 8/9: Nelene to schedule a meeting with stakeholders to discuss the process after the extract has been distributed (Mamello will advise when this may be done after discussion pertaining to volumes with Dewald) | Nelene |  |  | Open
3 | Process required when a new Impersonal account is opened | Suzette/MM/Shantha | 14/9/2020: 1. CIB have given us contact details 2. Lauretta has engaged with Suzette 3. RBB still finalising I&S 16/9/2020: 1. Suzette will advise by COB Friday 2. Minothi to contact Ryan Folster to find out if there can be a process for when new impersonal accounts are opened for any cluster, can they automatically notify GAML. Also ask him whether only GBS will be allowed to open impersonal account numbers for all cluster. Ask him about suspense account numbers as well. 3. Shantha indicated he will advise who will notify GAML of whether the account needs to be considered for IFTR reporting i.e. whether funds could have been transferred to an undelrying account 22/9/2020: 1. Suzette has still not advised - LM to esclate to Elena, Ilse and Surekha 2. MM still needs to engage with Ryna | Fri, 25th Sep | Open
4 | SWIFT Transactions - issues with identifying underlying client's account number from SWIFT message
4.1 | Melissa to send Shantha examples | Melissa | Done |  | Closed
4.2 | Melissa to investigate to see if there is an issue with extra spaces that could be rectified | Melissa | 14/9/2020: Melissa to provide feedback by tomorrow 22/09/2020: 1. Melissa has invetigated and identified an issue which has been resolved and the code has been updated 2. Waiting for a rerun to test this | Mon, 28th Sep | Open
4.3 | Notify Tlalane that Bash advised that the bank's strategy is to move towards automation - She must notify the SWIFT team must work towards rectifying misplaced data on SWIFT message | Minothi | 14/9/2020: 1. MM notified TN 2. Ilse advised that it is very difficult for project to tell SWIFT team what they need to do to get their stuff automated - TN, IB need to bring this to GAML's attention as this is not a project deliverable 3. Item to be kept open until meeting with GAML is held and they take ownership to drive this change 22/09/2020: 1. To be discussed with GAML next Monday | Tues, 29th Sep | Open
5 | RBB to engage with Bradley and Jackie regarding Corporate Saver | Shantha | 14/9/2020: 1. Shantha advised that he will confirm which transactions belong to RBB and which CIB and provide feedback 2. Shantha advised that he met with Corp Saver today and that it will be carried over till next week | Mon, 21st Sep | Open
6 | Process is required when an exception is routed to the business | Nelene |  | Mon, 28th Sep | Open
7 | MFC Impersonal Account transactions
7.1 | Melissa to investigate whether she can identify MFC accounts via product code | Melissa/MM | 14/09/2020: 1. Melissa to provide feedback by COB 16/09/2020: 1. Melissa has provided feedback and Eric has provided feedback that the code is available in NDW 2. The account numbers provided were MFC CA - Minothi to confirm whether this is one of the 12 account numbers provided by the FINSURV team - if yes, FINSURV team would handle the exception and provide underlying client's details (MM still to confirm with regarding to FINSURV Outgoing team about all 12 account numbers) - covered under point 22/09/2020: 1. MM advised that the account number is not one of the 12 that the FINSURV team would be managing 2. MM has contacted Eric as CTR has a solution for identifying underlying clients for impersonal accounts - awaiting criteria from Eric | Fri, 25th Sep | Open
7.2 | Melissa to investigate GPS Out file to see if the underlying client's account number is the file | Melissa | 14/09/2020: 1. Melissa will be sending out an email to Tlalane and team as the GPS out file still contains impersonal accounts - TN and MC to meet to discuss for them to investigate 22/09/2020: 1. Melissa to chat to Tlalane pertaining to engagements with the GPS team to get their input | 1st Oct | Open
8 | Card Settlement/Project transactions
8.1 | Melissa to send Shantha CMA EFT card settlement transactions in order for him to investigate | Melissa | 14/09/2020: 1. Melissa to send one file to cover all suspense and impersonal account transactions for CMS EFT - this will cover item 12.1 2. Melissa advised that CPS and ACB completed - she just needs to engage with Shantha regarding fields he requires 16/9/2020: Shantha received the files this morning - item closed | Tues, 15th Sep | Closed
8.2 | Shantha to engage with the card team to establish which account numbers are used purely for settlement purposes | Shantha | 14/09/2020: 1. Shanta advised to not go with account numbers as there are some account numbers which are used for both settlement and have underlying clients 2. Shantha advised that he is engaging with Card to understand which account numbers are being used purely settlement purposes 3. Ilse advised that Shantha need to engage with Card to understand which card account numbers are being used purely for settlement purposes 4. MM indicated that the card team should be able to provide which settlement accounts are being used purely for settlement and those being used for dual purpose 5. Davin asked to have a focussed call to discuss this - Davin to advise who from CARD to invite and will set up the meeting | Thurs, 17th Sep | Open
9 | GBS transactions - project team to engage with GBS to understand their transactions | Phakamile | 16/09/2020: 1. MM indicated that the GBS team confirmed that it is out of scope as GBS transactions would never have underlying accounts 2. PZ investigated how to identify GBS transactions in NDW - she has referred this to another analyst within NDW 22/09/2020: 1. PZ has provided us with the table name and she will provide us with the field names of the profit code 2. MM send an email to Shantha to ask him about how to identify a transactions profit code | Wed, 23rd Sep | Open | 49
10 | CIB Corp Saver - Minothi to set up session with Shantha, Eric and Melissa to unpack further | Shantha | 16/09/2020: Shantha to have meeting and advise whether RBB and CIB will need to resolve who is owning the transactions as the transaction will be routed to them. | Fri, 18th Sep | Open
11 | Other Cluster transactions - Minothi to investigate | Minothi | 16/09/2020: 1. Wealth: MM to check account numbers against Eric's/Issack's list of impersonal account numbers 2: CIB: Melissa to advise on account category and client type 22/9/2020: 1. Harry to find original email as MM investigations show that the account numbers do belong to Wealth - confirmed against the list provided by Wealth head of finance 2. MC has advised on client type. Engaged with Eric about account category - Eric requested examples from CIB -CIB has sent through the examples. Eric invesigating in NDW . | Fri, 25th Sep | Open
12 | CMA EFT Suspense account transactions
12.1 | Melissa to send Shantha CPS, MG and ACB GL suspense account transactions | Melissa | Closed on 16/9/2020 |  | Closed
12.2 | Shantha will advise with regards to CMA EFT GL settlement transactions that being with a 9 would have an underlying clients | Shantha | 16/9/2020: Shantha advised that this is in progress | TBC | Open
13 | FINSURV Exceptions: Shantha to advise which business areas these impersonal account transactions need to be routed to | Shantha | 16/9/2020: 1. Shantha advised that this item is In progress 2. Ilse advised that the transaction exceptions would be sent via email but in future it will possibly be via.GATR (Shantha asked to confirm with Bash) | TBC | Open
14 | CMA EFT: Shantha to advise which business areas CPS, MG and ACB exceptions need to be routed to | Shantha | 16/9/2020: 1. Shantha advised that this item is In progress 2. Ilse advised that the transaction exceptions would be sent via email but in future it will possibly be via.GATR (Shantha asked to confirm with Bash) | TBC | Open
15 | List of fields on Impersonal account exceptions report
15.1 | Minothi to engage with Melissa to confirm fields on current FIC report | Minothi | 16/9/2020: 1. Minothi indicated that this is in progress 22/9/2020: 1. Melissa and MM have met and this item is in progress | Fri, 25th Sep | Open
15.2 | Minothi to send file that was agreed with the other clusters to Shantha | Minothi | 16/9/2020: 1. Minothi indicated that this is in progress | TBC | Open
15.3 | Shantha to confirm list of fields RBB require with the RBB business areas | Shantha | 16/9/2020 Shantha awaiting file from Minothi | TBC | Open

## 12Oct20 (hidden)
IFTR DSU - 14 October 2020
Reporting Category / Issue | Task | Outstanding task/Progress | Responsibility | Date to complete | Blockers/Escalation | Comments
Bopcus/Non-reportable | Requirements | Requirements N/A
| Write up (GAML/GL) | Writes | Surekha | 15/10/2020 |  | Approval granted on 15/10 for the MCA SWIFT Write
| Mapping | Development | Melissa | 2020-10-21 |  | 16/10 Dev started today. 21/10 Dev completed test data to be sent out by EOD
| Development | Not applicable |  |  |  | Updated
| Testing | Regression testing for comments node | CIB: Ravi/Lakshmi RBB: Nkateko/Ntsoaki | 2020-10-23 | RBB/Wealth testing to be planned and executed | Non-reportable - exceptions testing in and out execution progress. Other testing done, Harry to provided formal feedback.21/10Testing team to start testing the MCA FACTS
| Defect |  |  | 15/10/2020
Testing to be conluded by Friday. Suspense acc requirement still pending
Bopcard Resident | Requirements | Not applicable
| Write up (GAML/GL) | Not applicable
| Mapping | Not applicable
| Development | Not applicable
| Testing | In progress | Harry/Tlalane | 2020-10-16 | Feedback FROM shanta | Testing concluded, Query raised on the account status field showing a code for closed account.
Defect
Bopcard Non-resident | Requirements | Requirements N/A |  |  |  | Done
| Write up (GAML/GL) | Write up - Low volumes to Grp AML | Tlalane/Group AML | 2020-10-16 | Acces GBM | Low volumes write submitted and approved by Group AML.
| Mapping | Development | Phakamile/Minothi/Melissa | 2020-09-29 | Acces to Dev enviroment | Curency code dev to complete inward leg delayed. Project team to meet with NDW to find a way forward
|  | Testing | Harry |  | CAMS source file | TRS Logged, Aadil doesn’t generate source. Referred to another team. Testing team to log an IM for the CAMS file to be landed in layer 0
| Development | In progress pending Gideons meetup (Phakaimile, Melissa, Minothi) | Melissa |  |  | Done
| Testing | Test data shared on the 1st Sep | Harry | 2020-10-09 | Source file | Zain has No capacity to help. IFTR PM requested to log an IM of rthe CAMS data to prioritised, NDW suggested we get access to Natteza. Harry has log a TRS.21/10 Project team battling to get hold of Zain for IM info. Peter and LM to the area manager
Defect
CMA - ACB | Requirements | Requirement N/A
| Write up (GAML/GL) | Write up -
| Mapping | Interbank sequence | Minothi |  |  | This is an industry wide problem
| Development | Development | Melissa | 2020-10-09 | Access still not granted | CIM900 Dev completed and test data shared with testing team 16/10.
| Testing | In progress | Nkateko |  |  | Certain fields are still not pulling through. Testing team to provide Melissa with screen shots and transction numbers
| Defect | Testing | Finsurv | In and out 85% | Suspense acc requirement /data issues | 1. Date issue pick up is a source issue 2. Address /city name also a data misalignment issue. Reason field/ FIU. Feedback received from the FIC 16/10. Ifo not quite useful. NDW requested PM to confirm which version of the FIC schema was used to provide feedbck. Testing team to provide Melissa with screen shots and transction numbers
CMA - CPS | Requirements | Requirements N/A
| Write up (GAML/GL) | Write Up N/a
| Mapping | Mappings | Clusters/NDW |  |  | suspense acc
| Development | Development | NDW | 2020-10-09 | Access still not granted | CIM900 Dev completed and test data shared with testing team 16/10
| Testing | Testing | Ntsoaki | TBA | address issue dependant on CIS and MDM misalignment . Reversals issue dependant on the FIC | 1. Date issue pick up is a source issue 2. Address /city name also a data misalignment issue. Reason field/ FIU. Feedback received from the FIC 16/10. Ifo not quite useful. NDW requested PM to confirm which version of the FIC schema was used to provide feedbck. Testing team to provide Melissa with screen shots and transction numbers |  | K33:L34H26K32:L33K33:L35H26K32:L33K33:K37H26K32:L33
| Defect |  |  |  | Suspense acc requirement /data issues | 2 defects to be addressed (covered under suspense and impersonal accounts) | EXCEPTIONS
CMA - Magtape | Requirements | Requirements N/A
| Write up (GAML/GL) | Not applicable
| Mapping | Address/city name not in CIS - but need to go to exceptions. |  | TBA |  | Need to wait for clusters to fix
| Development | In progress | Melissa | 2020-10-16 |  | CIM900 Dev completed and test data shared with testing team 16/10
| Testing | In progress | Harry |  |  | 1. Date issue pick up is a source issue 2. Address /city name also a data misalignment issue. Reason field/ FIU. Feedback received from the FIC 16/10. Ifo not quite useful. NDW requested PM to confirm which version of the FIC schema was used to provide feedbck. Testing team to provide Melissa with screen shots and transction numbers
| Defect |  |  |  | Suspense acc requirement /data issues | TRS log for the source file . PM reached out to the team manager Catherine, se has confirmed she has no capacity to look at the request at te stage but IFTR to touch base with her on Friday 16/10 to see what she can move to accommodate her.
Impersonal accounts | Requirements | 1. RBB - List of items to be addressed |  |  |  | Meeting to discuss with Davin on Monday. To discuss items on list
|  | 2. CIB - to check Shantha's examples against latest rules to establish if these transactions will be an issue | Minothi | 2020-10-12 |  | MM to request additional fields to check | CPS
|  | 3. Wealth - Followed up with Elena as to who will notify GAML of new impersonal accounts | Minothi |  |  | Still to confirm; waitng feedback. LM to escalate
| Write up (GAML/GL) | 1. An addendum to be added once the requirements are finalised | Minothi |  |  | Will be donet when All RBB requirements are complete. Weath to advise notification process to RBB
| Mapping | 1. Mappings to be updated when the requirements are finalised | Minothi
Development
Testing
| Defect | 1. Review of current defect list | Entire team
Suspense accounts | Requirements | 1. CPS, MG and ACB RBB suspense accounts to be investigated to indicate whether they would have underlying clients | Shantha |  |  | Shanta to request assistance from MC - Minothi to be included in meeting
| Write up (GAML/GL) | 1. An addendum to be added once the requirements are finalised | Minothi
Mapping
| Development | Development to take place after finalisation of the mapping update | Melissa
Testing
Defect
CMA Bank Statements | Mappings | 1. Investigate NDW data fields | Phakamile |  |  | Final document to be sent out today. Awaiting RBB feedback
|  | 2. Update mappings and distribute for sign-off | Minothi |  |  | Final document to be sent out today
China Systems | Mapping | 1. Engaging with China Systems team to understand transactions | Minothi/Tlalane |  |  | Need to obtain underlying client email (LM)
| Development | Development for China Systems transactions per mappings | Melissa
| Testing | Regression testing for completed development | TBA
Tracibility matrix | Requirements | 1. Waiting for GAML to load FIC presentations onto sharepoint | GAML |  |  | GAML to load FIC documents on Sharepoint.
|  | 2. Minothi to work on compiling spreadsheet | Minothi |  |  | GAML to load FIC documents on Sharepoint.
Independent testing | Bopcus |  | Peter |  |  | LM to chat to PS re independent testing
| Non reportable |  | Peter
| Bopcard Resident | In progress | Peter |  |  | Script to be finalised and testing to be completed by 14/10
| Bopcard Non-resident |  | Peter
| CMA - ACB | Completed | Peter |  |  | N/A
| CMA - CPS | Completed | Peter |  |  | N/A
| CMA - Magtape | Completed | Peter |  |  | N/A
ROA exceptions - across all reporting categories | All categories | Resolve whether clients should be included for reporting per the current rule set | Nelene |  |  | Meeting held with clusters. Clusters requested rerun - LM to request with MC. NL to update what is needed.
Exceptions management process | All categories | 1. Resolve Finsurv and CMA category financial exceptions process | Nelene |  |  | IB to escalate. LM did communicate on 9/10. Need to have a meeting for NS this week
|  | 2. Resolve cluster client exceptions process | Nelene |  |  | RBB to finalise where exceptions will flow
Country prefix code | All categories | Current proposed solution will not solve for the issue. Clusters to provide alternative solution | Clusters |  |  | Clusters to provide way forward on this. Is this being resolved through the MDM fixes?
Solution design | All categories | IER status - IB to update current document and distribute to Group AML and Group Legal | Ilse |  |  | Ilse to complete write-up on inclusion of IER status for Bopcus
Data lineage | All categories | Confirmation of hand-over to Group AML | Lauretta | Completed |  | Email sent to stakeholders
|  | Analysis hand over to Group AML team | Lauretta | Completed
CIS/MDM migration |  | Testing of exceptions to be completed | Testing team |  |  | Cluster have requested data for this investigtion
GATR exceptions automation |  | Development of GATR exceptions process flow | Eric /Adaptris |  | Dependent on completion of exceptions process | IB to follow up with Adaptris on IA
Breach process |  | Not at this time | Nelene |  |  | Process has been reviewed and updated. Final review and approval once reporting categories are finalised
Passport/ID no blank |  | Defect to be closed? |  |  |  | ME team to review whether this is a capturing issue. NS to follow up on this. A CVH issue, not ME onboarding. RBB to follow up to close this issue
FIU message |  | Group AML has escalated to FIC. Awaiting feedback | Group AML | TBA | FIC | Matter raised with Group AML
Dormant accounts /GL account |  | To be resolved for RBB - escalation to Group AML required | Ilse / Group AML | TBA |  | RBB - Need to resolve with Bash on way forward. Finsurv team will deal with exceptions. Shanta to advise whether this could be an issue for CMA transactions
Approval of testing by clusters | Testing sign-off by clusters | Complete testing Complete traceability matrix Obtain sign-off | Peter / Testing team
Methodology register | Register of changes required to the methodology | First draft of registrer completed Update as an when required Provide to Group AML for update of methodology document | Lauretta / Group AML |  |  | Register shared with Group AML
Financial reconciliations | 3 way recon for IFTR | Complete hand-over from James Vlok to Group Finance Complete 3 way recon and obtain approval Implement 3 way recon for IFTR | Lachelle van der Merwe / Group Finance / NDW | TBA |  | GF workshop on Friday 11/9. Have requested weekly update on progress. IB to follow up on progress
No | Action Items | Responsible | Feedback/Notes | Next follow up date | Status | Defect No
1 | SWIFT Inflow - Lauretta and Tlalane to engage with Mamello on this | LM/TN | 14/9/2020: 1. TN has updated mappings to include IER status and they do have it on BOPCUS for certain transactions. FINSURV team indicated that we need to include IER for BOPCUS. 2. TL and LB to engage with Mamello by COB 16/9 - LM asked to keep this item open till then 22/9/2020: 1. LM has advised that the mappings were updated and that this item should be closed | Thurs, 17th Sep | Closed
2 | SWIFT Outflow - Meeting with Mamello and FINSURV team
2.1 | SWIFT Outflow - Meeting with Mamello and FINSURV team to be held to discuss this | MC | 14/9/2020: 1. Meeting was held on 8/9 to confirm which account numbers the outgoing team would manage 2. Mamello requested dataand indicated that previous extract would suffice but she then requested Aug data - Minothi to confirm with Mamello as whether a new extract is required 16/9/2020: 1. Mamello confirmed that she wants a new extract for August so that it can be distributed to the team for them to advise on the acocunt numbers 2. See 2.3 below | Refer to 2.3 below | Open
2.2. | Meeting on 8/9: Mamello to send an email pertaining to the descriptions she requires on the exception report | Mamello | Mamello has discussed this with Melissa |  | Closed
2.3 | Meeting on 8/9: 2. Melissa to then run an extract for August 2020 to extract the outgoing FINSURV impersonal and suspense account exceptions (this would include all impersonal accounts and not be limited to the list that the incoming team provided) – the following account numbers need to be excluded as they would only be applicable to domestic transactions: 1565000218, 1565000226, 1565000234, 1565000242 The extract to include the descriptions provided by Mamello. | MC | 22/09/2020: 1. Melissa has run the extrat for the data that is available in NDW 2. Mamello has some queries pertaining to the data range as it is not for the 1st Aug - 31st Aug - Melissa has advised that the GPS data is not available in NDW for that date range 3. MC will respond to Mamello's addtional queries. |  | Open
2.4 | Meeting on 8/9: 3. Melissa to distribute the file to Mamello and the project team | MC |  |  | Open
2.5 | Meeting on 8/9: Mamello to send the file to all stakeholders and Dewald to obtain input. The team will also confirm whether we must send all the impersonal account exceptions to them or whether there is a list of accounts that is specific to the outgoing transactions team - this item will also answer Shantha's query about the MFC account number | Mamello |  |  | Open
2.6 | Mtng on 8/9:Minothi to set up meeting with Suzette Steyn and Linda Botman from Cape Town | MM | 22/09/2020: Meeting scheduled for 22/9/2020 with CT stakeholders to discuss exceptions and account numbers that the CT outgoing exceptions team will handle |  | Open
2.7 | Mtng on 8/9: Nelene to schedule a meeting with stakeholders to discuss the process after the extract has been distributed (Mamello will advise when this may be done after discussion pertaining to volumes with Dewald) | Nelene |  |  | Open
3 | Process required when a new Impersonal account is opened | Suzette/MM/Shantha | 14/9/2020: 1. CIB have given us contact details 2. Lauretta has engaged with Suzette 3. RBB still finalising I&S 16/9/2020: 1. Suzette will advise by COB Friday 2. Minothi to contact Ryan Folster to find out if there can be a process for when new impersonal accounts are opened for any cluster, can they automatically notify GAML. Also ask him whether only GBS will be allowed to open impersonal account numbers for all cluster. Ask him about suspense account numbers as well. 3. Shantha indicated he will advise who will notify GAML of whether the account needs to be considered for IFTR reporting i.e. whether funds could have been transferred to an undelrying account 22/9/2020: 1. Suzette has still not advised - LM to esclate to Elena, Ilse and Surekha 2. MM still needs to engage with Ryna | Fri, 25th Sep | Open
4 | SWIFT Transactions - issues with identifying underlying client's account number from SWIFT message
4.1 | Melissa to send Shantha examples | Melissa | Done |  | Closed
4.2 | Melissa to investigate to see if there is an issue with extra spaces that could be rectified | Melissa | 14/9/2020: Melissa to provide feedback by tomorrow 22/09/2020: 1. Melissa has invetigated and identified an issue which has been resolved and the code has been updated 2. Waiting for a rerun to test this | Mon, 28th Sep | Open
4.3 | Notify Tlalane that Bash advised that the bank's strategy is to move towards automation - She must notify the SWIFT team must work towards rectifying misplaced data on SWIFT message | Minothi | 14/9/2020: 1. MM notified TN 2. Ilse advised that it is very difficult for project to tell SWIFT team what they need to do to get their stuff automated - TN, IB need to bring this to GAML's attention as this is not a project deliverable 3. Item to be kept open until meeting with GAML is held and they take ownership to drive this change 22/09/2020: 1. To be discussed with GAML next Monday | Tues, 29th Sep | Open
5 | RBB to engage with Bradley and Jackie regarding Corporate Saver | Shantha | 14/9/2020: 1. Shantha advised that he will confirm which transactions belong to RBB and which CIB and provide feedback 2. Shantha advised that he met with Corp Saver today and that it will be carried over till next week | Mon, 21st Sep | Open
6 | Process is required when an exception is routed to the business | Nelene |  | Mon, 28th Sep | Open
7 | MFC Impersonal Account transactions
7.1 | Melissa to investigate whether she can identify MFC accounts via product code | Melissa/MM | 14/09/2020: 1. Melissa to provide feedback by COB 16/09/2020: 1. Melissa has provided feedback and Eric has provided feedback that the code is available in NDW 2. The account numbers provided were MFC CA - Minothi to confirm whether this is one of the 12 account numbers provided by the FINSURV team - if yes, FINSURV team would handle the exception and provide underlying client's details (MM still to confirm with regarding to FINSURV Outgoing team about all 12 account numbers) - covered under point 22/09/2020: 1. MM advised that the account number is not one of the 12 that the FINSURV team would be managing 2. MM has contacted Eric as CTR has a solution for identifying underlying clients for impersonal accounts - awaiting criteria from Eric | Fri, 25th Sep | Open
7.2 | Melissa to investigate GPS Out file to see if the underlying client's account number is the file | Melissa | 14/09/2020: 1. Melissa will be sending out an email to Tlalane and team as the GPS out file still contains impersonal accounts - TN and MC to meet to discuss for them to investigate 22/09/2020: 1. Melissa to chat to Tlalane pertaining to engagements with the GPS team to get their input | 1st Oct | Open
8 | Card Settlement/Project transactions
8.1 | Melissa to send Shantha CMA EFT card settlement transactions in order for him to investigate | Melissa | 14/09/2020: 1. Melissa to send one file to cover all suspense and impersonal account transactions for CMS EFT - this will cover item 12.1 2. Melissa advised that CPS and ACB completed - she just needs to engage with Shantha regarding fields he requires 16/9/2020: Shantha received the files this morning - item closed | Tues, 15th Sep | Closed
8.2 | Shantha to engage with the card team to establish which account numbers are used purely for settlement purposes | Shantha | 14/09/2020: 1. Shanta advised to not go with account numbers as there are some account numbers which are used for both settlement and have underlying clients 2. Shantha advised that he is engaging with Card to understand which account numbers are being used purely settlement purposes 3. Ilse advised that Shantha need to engage with Card to understand which card account numbers are being used purely for settlement purposes 4. MM indicated that the card team should be able to provide which settlement accounts are being used purely for settlement and those being used for dual purpose 5. Davin asked to have a focussed call to discuss this - Davin to advise who from CARD to invite and will set up the meeting | Thurs, 17th Sep | Open
9 | GBS transactions - project team to engage with GBS to understand their transactions | Phakamile | 16/09/2020: 1. MM indicated that the GBS team confirmed that it is out of scope as GBS transactions would never have underlying accounts 2. PZ investigated how to identify GBS transactions in NDW - she has referred this to another analyst within NDW 22/09/2020: 1. PZ has provided us with the table name and she will provide us with the field names of the profit code 2. MM send an email to Shantha to ask him about how to identify a transactions profit code | Wed, 23rd Sep | Open | 49
10 | CIB Corp Saver - Minothi to set up session with Shantha, Eric and Melissa to unpack further | Shantha | 16/09/2020: Shantha to have meeting and advise whether RBB and CIB will need to resolve who is owning the transactions as the transaction will be routed to them. | Fri, 18th Sep | Open
11 | Other Cluster transactions - Minothi to investigate | Minothi | 16/09/2020: 1. Wealth: MM to check account numbers against Eric's/Issack's list of impersonal account numbers 2: CIB: Melissa to advise on account category and client type 22/9/2020: 1. Harry to find original email as MM investigations show that the account numbers do belong to Wealth - confirmed against the list provided by Wealth head of finance 2. MC has advised on client type. Engaged with Eric about account category - Eric requested examples from CIB -CIB has sent through the examples. Eric invesigating in NDW . | Fri, 25th Sep | Open
12 | CMA EFT Suspense account transactions
12.1 | Melissa to send Shantha CPS, MG and ACB GL suspense account transactions | Melissa | Closed on 16/9/2020 |  | Closed
12.2 | Shantha will advise with regards to CMA EFT GL settlement transactions that being with a 9 would have an underlying clients | Shantha | 16/9/2020: Shantha advised that this is in progress | TBC | Open
13 | FINSURV Exceptions: Shantha to advise which business areas these impersonal account transactions need to be routed to | Shantha | 16/9/2020: 1. Shantha advised that this item is In progress 2. Ilse advised that the transaction exceptions would be sent via email but in future it will possibly be via.GATR (Shantha asked to confirm with Bash) | TBC | Open
14 | CMA EFT: Shantha to advise which business areas CPS, MG and ACB exceptions need to be routed to | Shantha | 16/9/2020: 1. Shantha advised that this item is In progress 2. Ilse advised that the transaction exceptions would be sent via email but in future it will possibly be via.GATR (Shantha asked to confirm with Bash) | TBC | Open
15 | List of fields on Impersonal account exceptions report
15.1 | Minothi to engage with Melissa to confirm fields on current FIC report | Minothi | 16/9/2020: 1. Minothi indicated that this is in progress 22/9/2020: 1. Melissa and MM have met and this item is in progress | Fri, 25th Sep | Open
15.2 | Minothi to send file that was agreed with the other clusters to Shantha | Minothi | 16/9/2020: 1. Minothi indicated that this is in progress | TBC | Open
15.3 | Shantha to confirm list of fields RBB require with the RBB business areas | Shantha | 16/9/2020 Shantha awaiting file from Minothi | TBC | Open

## 26Oct20 (hidden)
IFTR DSU - 26 October 2020
Reporting Category / Issue | Task | Outstanding task/Progress | Responsibility | Date to complete | Blockers/Escalation | Comments
Bopcus/Non-reportable | Requirements | Requirements N/A
| Write up (GAML/GL) | Writes | Surekha | 15/10/2020
| Mapping | Development | Melissa | 2020-10-21 |  | FACTS - missing account numbers, BA and Dev to investigate
| Development | Not applicable |  |  |  | TBA on investigation
| Testing | Regression testing for comments node | CIB: Ravi/Lakshmi RBB: Nkateko/Ntsoaki | 2020-10-23 | RBB/Wealth testing to be planned and executed | Retesting of statuses for GPS. Concluding today
| Defect |  |  | 15/10/2020
?
Bopcard Resident | Requirements | Not applicable
| Write up (GAML/GL) | Not applicable
| Mapping | Not applicable
| Development | Not applicable
| Testing | In progress | Harry/Tlalane | 2020-10-16 | Feedback FROM shanta | Waiting for completion of other categories before retesting
Defect
Bopcard Non-resident | Requirements | Requirements N/A |  |  |  | Done
| Write up (GAML/GL) | Write up - Low volumes to Grp AML | Tlalane/Group AML | 2020-10-16 | Acces GBM | Low volumes write submitted and approved by Group AML.
| Mapping | Development | Phakamile/Minothi/Melissa | 2020-09-29 | Acces to Dev enviroment | Need table in ODS for country code. Talking to CAMS to resolve
|  | Testing | Harry |  | CAMS source file | Session at 12 to get the data required for the extract
| Development | In progress pending Gideons meetup (Phakaimile, Melissa, Minothi) | Melissa |  |  | Waiting for the table to land in ODS
| Testing | Test data shared on the 1st Sep | Harry | 2020-10-09 | Source file | Session at 12 to get the data required for the extract
Defect
CMA - ACB | Requirements | Requirement N/A
| Write up (GAML/GL) | Write up -
| Mapping | Interbank sequence | Minothi |  |  | This is an industry wide problem
| Development | Development | Melissa | 2020-10-09 | Access still not granted
| Testing | In progress | Nkateko |  |  | 80%. Waiting for suspense&impersonal to complete testing
| Defect | Testing | Finsurv | In and out 85% | Suspense acc requirement /data issues | Write-up to be completed for 2 issues on ACB. MC to check file that lands in layer 0 to check on date issue (source or NDW issue) 2. Address /city name also a data misalignment issue. Group AML - Reason field/ FIU. Feedback received from the FIC 16/10. Group AML to discuss directly with the FIC - how do we close this out with Group AML. How to move to BAU?
CMA - CPS | Requirements | Requirements N/A
| Write up (GAML/GL) | Write Up N/a
| Mapping | Mappings | Clusters/NDW |  |  | suspense acc
| Development | Development | NDW | 2020-10-09 | Access still not granted
| Testing | Testing | Ntsoaki | TBA | address issue dependant on CIS and MDM misalignment . Reversals issue dependant on the FIC | 1. Date issue pick up is a source issue 2. Address /city name also a data misalignment issue. Reason field/ FIU. Feedback received from the FIC 16/10. Ifo not quite useful. NDW requested PM to confirm which version of the FIC schema was used to provide feedbck. Testing team to provide Melissa with screen shots and transction numbers |  | K33:L34H26K32:L33K33:L35H26K32:L33K33:K37H26K32:L33
| Defect |  |  |  | Suspense acc requirement /data issues | 2 defects to be addressed (covered under suspense and impersonal accounts) | EXCEPTIONS
CMA - Magtape | Requirements | Requirements N/A
| Write up (GAML/GL) | Not applicable
| Mapping | Address/city name not in CIS - but need to go to exceptions. |  | TBA |  | Need to wait for clusters to fix
| Development | In progress | Melissa | 2020-10-16 |  | CIM900 Dev completed and test data shared with testing team 16/10
| Testing | In progress | Harry |  |  | 1. Date issue pick up is a source issue 2. Address /city name also a data misalignment issue. Reason field/ FIU. Feedback received from the FIC 16/10. Ifo not quite useful. NDW requested PM to confirm which version of the FIC schema was used to provide feedbck. Testing team to provide Melissa with screen shots and transction numbers
| Defect |  |  |  | Suspense acc requirement /data issues | TRS log for the source file . PM reached out to the team manager Catherine, se has confirmed she has no capacity to look at the request at te stage but IFTR to touch base with her on Friday 16/10 to see what she can move to accommodate her.
Impersonal accounts | Requirements | 1. RBB - List of items to be addressed |  |  |  | Meeting to discuss with Davin on Monday. To discuss items on list
|  | 2. CIB - to check Shantha's examples against latest rules to establish if these transactions will be an issue | Minothi | 2020-10-12 |  | MM to request additional fields to check | CPS
|  | 3. Wealth - Followed up with Elena as to who will notify GAML of new impersonal accounts | Minothi |  |  | Still to confirm; waitng feedback. LM to escalate
| Write up (GAML/GL) | 1. An addendum to be added once the requirements are finalised | Minothi |  |  | Will be donet when All RBB requirements are complete. Weath to advise notification process to RBB
| Mapping | 1. Mappings to be updated when the requirements are finalised | Minothi
Development
Testing
| Defect | 1. Review of current defect list | Entire team
Suspense accounts | Requirements | 1. CPS, MG and ACB RBB suspense accounts to be investigated to indicate whether they would have underlying clients | Shantha |  |  | Shanta to request assistance from MC - Minothi to be included in meeting
| Write up (GAML/GL) | 1. An addendum to be added once the requirements are finalised | Minothi
Mapping
| Development | Development to take place after finalisation of the mapping update | Melissa
Testing
Defect
CMA Bank Statements | Mappings | 1. Investigate NDW data fields | Phakamile |  |  | Final document to be sent out today. Awaiting RBB feedback
|  | 2. Update mappings and distribute for sign-off | Minothi |  |  | Final document to be sent out today
China Systems | Mapping | 1. Engaging with China Systems team to understand transactions | Minothi/Tlalane |  |  | Need to obtain underlying client email (LM)
| Development | Development for China Systems transactions per mappings | Melissa
| Testing | Regression testing for completed development | TBA
Tracibility matrix | Requirements | 1. Waiting for GAML to load FIC presentations onto sharepoint | GAML |  |  | GAML to load FIC documents on Sharepoint.
|  | 2. Minothi to work on compiling spreadsheet | Minothi |  |  | GAML to load FIC documents on Sharepoint.
Independent testing | Bopcus |  | Peter |  |  | LM to chat to PS re independent testing
| Non reportable |  | Peter
| Bopcard Resident | In progress | Peter |  |  | Script to be finalised and testing to be completed by 14/10
| Bopcard Non-resident |  | Peter
| CMA - ACB | Completed | Peter |  |  | CIM900 access required to finalise
| CMA - CPS | Completed | Peter |  |  | CIM900 access required to finalise
| CMA - Magtape | Completed | Peter |  |  | CIM900 access required to finalise
ROA exceptions - across all reporting categories | All categories | Resolve whether clients should be included for reporting per the current rule set | Nelene |  |  | Meeting held with clusters. Clusters requested rerun - LM to request with MC. NL to update what is needed.
Exceptions management process | All categories | 1. Resolve Finsurv and CMA category financial exceptions process | Nelene |  |  | IB to escalate. LM did communicate on 9/10. Need to have a meeting for NS this week
|  | 2. Resolve cluster client exceptions process | Nelene |  |  | RBB to finalise where exceptions will flow
Country prefix code | All categories | Current proposed solution will not solve for the issue. Clusters to provide alternative solution | Clusters |  |  | Clusters to provide way forward on this. Is this being resolved through the MDM fixes?
Solution design | All categories | IER status - IB to update current document and distribute to Group AML and Group Legal | Ilse |  |  | Ilse to complete write-up on inclusion of IER status for Bopcus
Data lineage | All categories | Confirmation of hand-over to Group AML | Lauretta | Completed |  | Email sent to stakeholders
|  | Analysis hand over to Group AML team | Lauretta | Completed
CIS/MDM migration |  | Testing of exceptions to be completed | Testing team |  |  | Cluster have requested data for this investigtion
GATR exceptions automation |  | Development of GATR exceptions process flow | Eric /Adaptris |  | Dependent on completion of exceptions process | IB to follow up with Adaptris on IA
Breach process |  | Not at this time | Nelene |  |  | Process has been reviewed and updated. Final review and approval once reporting categories are finalised
Passport/ID no blank |  | Defect to be closed? |  |  |  | ME team to review whether this is a capturing issue. NS to follow up on this. A CVH issue, not ME onboarding. RBB to follow up to close this issue
FIU message |  | Group AML has escalated to FIC. Awaiting feedback | Group AML | TBA | FIC | Matter raised with Group AML
Dormant accounts /GL account |  | To be resolved for RBB - escalation to Group AML required | Ilse / Group AML | TBA |  | RBB - Need to resolve with Bash on way forward. Finsurv team will deal with exceptions. Shanta to advise whether this could be an issue for CMA transactions
Approval of testing by clusters | Testing sign-off by clusters | Complete testing Complete traceability matrix Obtain sign-off | Peter / Testing team
Methodology register | Register of changes required to the methodology | First draft of registrer completed Update as an when required Provide to Group AML for update of methodology document | Lauretta / Group AML |  |  | Register shared with Group AML
Financial reconciliations | 3 way recon for IFTR | Complete hand-over from James Vlok to Group Finance Complete 3 way recon and obtain approval Implement 3 way recon for IFTR | Lachelle van der Merwe / Group Finance / NDW | TBA |  | GF workshop on Friday 11/9. Have requested weekly update on progress. IB to follow up on progress
No | Action Items | Responsible | Feedback/Notes | Next follow up date | Status | Defect No
1 | SWIFT Inflow - Lauretta and Tlalane to engage with Mamello on this | LM/TN | 14/9/2020: 1. TN has updated mappings to include IER status and they do have it on BOPCUS for certain transactions. FINSURV team indicated that we need to include IER for BOPCUS. 2. TL and LB to engage with Mamello by COB 16/9 - LM asked to keep this item open till then 22/9/2020: 1. LM has advised that the mappings were updated and that this item should be closed | Thurs, 17th Sep | Closed
2 | SWIFT Outflow - Meeting with Mamello and FINSURV team
2.1 | SWIFT Outflow - Meeting with Mamello and FINSURV team to be held to discuss this | MC | 14/9/2020: 1. Meeting was held on 8/9 to confirm which account numbers the outgoing team would manage 2. Mamello requested dataand indicated that previous extract would suffice but she then requested Aug data - Minothi to confirm with Mamello as whether a new extract is required 16/9/2020: 1. Mamello confirmed that she wants a new extract for August so that it can be distributed to the team for them to advise on the acocunt numbers 2. See 2.3 below | Refer to 2.3 below | Open
2.2. | Meeting on 8/9: Mamello to send an email pertaining to the descriptions she requires on the exception report | Mamello | Mamello has discussed this with Melissa |  | Closed
2.3 | Meeting on 8/9: 2. Melissa to then run an extract for August 2020 to extract the outgoing FINSURV impersonal and suspense account exceptions (this would include all impersonal accounts and not be limited to the list that the incoming team provided) – the following account numbers need to be excluded as they would only be applicable to domestic transactions: 1565000218, 1565000226, 1565000234, 1565000242 The extract to include the descriptions provided by Mamello. | MC | 22/09/2020: 1. Melissa has run the extrat for the data that is available in NDW 2. Mamello has some queries pertaining to the data range as it is not for the 1st Aug - 31st Aug - Melissa has advised that the GPS data is not available in NDW for that date range 3. MC will respond to Mamello's addtional queries. |  | Open
2.4 | Meeting on 8/9: 3. Melissa to distribute the file to Mamello and the project team | MC |  |  | Open
2.5 | Meeting on 8/9: Mamello to send the file to all stakeholders and Dewald to obtain input. The team will also confirm whether we must send all the impersonal account exceptions to them or whether there is a list of accounts that is specific to the outgoing transactions team - this item will also answer Shantha's query about the MFC account number | Mamello |  |  | Open
2.6 | Mtng on 8/9:Minothi to set up meeting with Suzette Steyn and Linda Botman from Cape Town | MM | 22/09/2020: Meeting scheduled for 22/9/2020 with CT stakeholders to discuss exceptions and account numbers that the CT outgoing exceptions team will handle |  | Open
2.7 | Mtng on 8/9: Nelene to schedule a meeting with stakeholders to discuss the process after the extract has been distributed (Mamello will advise when this may be done after discussion pertaining to volumes with Dewald) | Nelene |  |  | Open
3 | Process required when a new Impersonal account is opened | Suzette/MM/Shantha | 14/9/2020: 1. CIB have given us contact details 2. Lauretta has engaged with Suzette 3. RBB still finalising I&S 16/9/2020: 1. Suzette will advise by COB Friday 2. Minothi to contact Ryan Folster to find out if there can be a process for when new impersonal accounts are opened for any cluster, can they automatically notify GAML. Also ask him whether only GBS will be allowed to open impersonal account numbers for all cluster. Ask him about suspense account numbers as well. 3. Shantha indicated he will advise who will notify GAML of whether the account needs to be considered for IFTR reporting i.e. whether funds could have been transferred to an undelrying account 22/9/2020: 1. Suzette has still not advised - LM to esclate to Elena, Ilse and Surekha 2. MM still needs to engage with Ryna | Fri, 25th Sep | Open
4 | SWIFT Transactions - issues with identifying underlying client's account number from SWIFT message
4.1 | Melissa to send Shantha examples | Melissa | Done |  | Closed
4.2 | Melissa to investigate to see if there is an issue with extra spaces that could be rectified | Melissa | 14/9/2020: Melissa to provide feedback by tomorrow 22/09/2020: 1. Melissa has invetigated and identified an issue which has been resolved and the code has been updated 2. Waiting for a rerun to test this | Mon, 28th Sep | Open
4.3 | Notify Tlalane that Bash advised that the bank's strategy is to move towards automation - She must notify the SWIFT team must work towards rectifying misplaced data on SWIFT message | Minothi | 14/9/2020: 1. MM notified TN 2. Ilse advised that it is very difficult for project to tell SWIFT team what they need to do to get their stuff automated - TN, IB need to bring this to GAML's attention as this is not a project deliverable 3. Item to be kept open until meeting with GAML is held and they take ownership to drive this change 22/09/2020: 1. To be discussed with GAML next Monday | Tues, 29th Sep | Open
5 | RBB to engage with Bradley and Jackie regarding Corporate Saver | Shantha | 14/9/2020: 1. Shantha advised that he will confirm which transactions belong to RBB and which CIB and provide feedback 2. Shantha advised that he met with Corp Saver today and that it will be carried over till next week | Mon, 21st Sep | Open
6 | Process is required when an exception is routed to the business | Nelene |  | Mon, 28th Sep | Open
7 | MFC Impersonal Account transactions
7.1 | Melissa to investigate whether she can identify MFC accounts via product code | Melissa/MM | 14/09/2020: 1. Melissa to provide feedback by COB 16/09/2020: 1. Melissa has provided feedback and Eric has provided feedback that the code is available in NDW 2. The account numbers provided were MFC CA - Minothi to confirm whether this is one of the 12 account numbers provided by the FINSURV team - if yes, FINSURV team would handle the exception and provide underlying client's details (MM still to confirm with regarding to FINSURV Outgoing team about all 12 account numbers) - covered under point 22/09/2020: 1. MM advised that the account number is not one of the 12 that the FINSURV team would be managing 2. MM has contacted Eric as CTR has a solution for identifying underlying clients for impersonal accounts - awaiting criteria from Eric | Fri, 25th Sep | Open
7.2 | Melissa to investigate GPS Out file to see if the underlying client's account number is the file | Melissa | 14/09/2020: 1. Melissa will be sending out an email to Tlalane and team as the GPS out file still contains impersonal accounts - TN and MC to meet to discuss for them to investigate 22/09/2020: 1. Melissa to chat to Tlalane pertaining to engagements with the GPS team to get their input | 1st Oct | Open
8 | Card Settlement/Project transactions
8.1 | Melissa to send Shantha CMA EFT card settlement transactions in order for him to investigate | Melissa | 14/09/2020: 1. Melissa to send one file to cover all suspense and impersonal account transactions for CMS EFT - this will cover item 12.1 2. Melissa advised that CPS and ACB completed - she just needs to engage with Shantha regarding fields he requires 16/9/2020: Shantha received the files this morning - item closed | Tues, 15th Sep | Closed
8.2 | Shantha to engage with the card team to establish which account numbers are used purely for settlement purposes | Shantha | 14/09/2020: 1. Shanta advised to not go with account numbers as there are some account numbers which are used for both settlement and have underlying clients 2. Shantha advised that he is engaging with Card to understand which account numbers are being used purely settlement purposes 3. Ilse advised that Shantha need to engage with Card to understand which card account numbers are being used purely for settlement purposes 4. MM indicated that the card team should be able to provide which settlement accounts are being used purely for settlement and those being used for dual purpose 5. Davin asked to have a focussed call to discuss this - Davin to advise who from CARD to invite and will set up the meeting | Thurs, 17th Sep | Open
9 | GBS transactions - project team to engage with GBS to understand their transactions | Phakamile | 16/09/2020: 1. MM indicated that the GBS team confirmed that it is out of scope as GBS transactions would never have underlying accounts 2. PZ investigated how to identify GBS transactions in NDW - she has referred this to another analyst within NDW 22/09/2020: 1. PZ has provided us with the table name and she will provide us with the field names of the profit code 2. MM send an email to Shantha to ask him about how to identify a transactions profit code | Wed, 23rd Sep | Open | 49
10 | CIB Corp Saver - Minothi to set up session with Shantha, Eric and Melissa to unpack further | Shantha | 16/09/2020: Shantha to have meeting and advise whether RBB and CIB will need to resolve who is owning the transactions as the transaction will be routed to them. | Fri, 18th Sep | Open
11 | Other Cluster transactions - Minothi to investigate | Minothi | 16/09/2020: 1. Wealth: MM to check account numbers against Eric's/Issack's list of impersonal account numbers 2: CIB: Melissa to advise on account category and client type 22/9/2020: 1. Harry to find original email as MM investigations show that the account numbers do belong to Wealth - confirmed against the list provided by Wealth head of finance 2. MC has advised on client type. Engaged with Eric about account category - Eric requested examples from CIB -CIB has sent through the examples. Eric invesigating in NDW . | Fri, 25th Sep | Open
12 | CMA EFT Suspense account transactions
12.1 | Melissa to send Shantha CPS, MG and ACB GL suspense account transactions | Melissa | Closed on 16/9/2020 |  | Closed
12.2 | Shantha will advise with regards to CMA EFT GL settlement transactions that being with a 9 would have an underlying clients | Shantha | 16/9/2020: Shantha advised that this is in progress | TBC | Open
13 | FINSURV Exceptions: Shantha to advise which business areas these impersonal account transactions need to be routed to | Shantha | 16/9/2020: 1. Shantha advised that this item is In progress 2. Ilse advised that the transaction exceptions would be sent via email but in future it will possibly be via.GATR (Shantha asked to confirm with Bash) | TBC | Open
14 | CMA EFT: Shantha to advise which business areas CPS, MG and ACB exceptions need to be routed to | Shantha | 16/9/2020: 1. Shantha advised that this item is In progress 2. Ilse advised that the transaction exceptions would be sent via email but in future it will possibly be via.GATR (Shantha asked to confirm with Bash) | TBC | Open
15 | List of fields on Impersonal account exceptions report
15.1 | Minothi to engage with Melissa to confirm fields on current FIC report | Minothi | 16/9/2020: 1. Minothi indicated that this is in progress 22/9/2020: 1. Melissa and MM have met and this item is in progress | Fri, 25th Sep | Open
15.2 | Minothi to send file that was agreed with the other clusters to Shantha | Minothi | 16/9/2020: 1. Minothi indicated that this is in progress | TBC | Open
15.3 | Shantha to confirm list of fields RBB require with the RBB business areas | Shantha | 16/9/2020 Shantha awaiting file from Minothi | TBC | Open

## 27Oct20 (hidden)
IFTR DSU - 27 October 2020
Reporting Category / Issue | Task | Outstanding task/Progress | Responsibility | Date to complete | Blockers/Escalation | Comments
Bopcus/Non-reportable | Requirements | Requirements N/A
| Write up (GAML/GL) | N/A
| Mapping | FACTS - missing account number | Melissa | 2020-10-28 |  | FACTS - missing account numbers, BA and Dev to investigate - could be a timing issue - could require rerun of data
| Development | China Systems / Swift message | Melissa/Tlalane |  |  | TBA on investigation. Dev will be required for China Systems and for the Swift message (GPS in account numbers)
| Testing | Regression testing for comments node | CIB: Ravi/Lakshmi RBB: Nkateko/Ntsoaki |  | RBB/Wealth testing to be planned and executed | GPS status completed. No issues picked up. Will retest FACTS once resolved. Provide list of test cases to be completed here
Defect
Bopcard Resident | Requirements | Not applicable
| Write up (GAML/GL) | Not applicable
| Mapping | Not applicable
| Development | Not applicable
| Testing |  |  |  |  | Waiting for completion of other categories / S&I before retesting
Defect
Bopcard Non-resident | Requirements | Requirements N/A |  |  |  | Done
Write up (GAML/GL)
| Mapping | Development | Phakamile/Minothi/Melissa | 2020-10-28 | Access to GBM table | Need table in ODS for country code. Met with TRB to obtain approval for development on ODS. Exceptions file run - impersonal accounts found (2) and NMC - country code (flow out) blank is source - need to find source to look at data field
|  | Testing | Harry | 2020-10-28 | CAMS source file | Reviewed fields in data that was received. Finalise with Phakamile and see if the data is sufficient for use
| Development | Country code to derive currency | Melissa |  |  | Waiting for the table to land in ODS
| Testing | Data | Harry | 2020-10-28 | Source file | Reviewed fields in data that was received. Finalise with Phakamile and see if the data is sufficient for use
Defect
CMA - ACB | Requirements | Requirement N/A
| Write up (GAML/GL) | Write up - |  |  |  | Write-up to be completed for 2 issues on ACB. MC to check file that lands in layer 0 to check on date issue (source or NDW issue)
| Mapping | Interbank sequence | Minothi |  |  | This is an industry wide problem - Write up to Group AML on way forward
| Development | Development | Melissa |  |  | Dependent on outcome of Group AML feedback
| Testing | In progress | Nkateko |  |  | 80%. Waiting for suspense&impersonal to complete testing
| Defect | Testing | Minothi | In and out 85% | Suspense acc requirement /data issues | Address /city name also a data misalignment issue. Group AML - Reason field/ FIU. Feedback received from the FIC 16/10. Group AML to discuss directly with the FIC - how do we close this out with Group AML. How to move to BAU?
CMA - CPS | Requirements | Requirements N/A
| Write up (GAML/GL) | Write Up N/a
| Mapping | Mappings | Clusters/NDW
| Development | Development | NDW
| Testing | Testing | Ntsoaki |  |  | 2. Address /city name also a data misalignment issue. Reason field/ FIU. Feedback received from the FIC 16/10. Ifo not quite useful. NDW requested PM to confirm which version of the FIC schema was used to provide feedbck. Testing team to provide Melissa with screen shots and transction numbers. CPS - Swift code loaded as 0 - need data access here (PS) - MC to assist with view of file
| Defect |  |  |  | Suspense acc requirement /data issues | 2 defects to be addressed (covered under suspense and impersonal accounts). Rounding issue with account numbers (meeting with Charl to resolve). Shanta - email 22/10 - look at issue and respond (MC/Nelene)
CMA - Magtape | Requirements | Requirements N/A
| Write up (GAML/GL) | Not applicable
| Mapping | Address/city name not in CIS - but need to go to exceptions. |  | TBA |  | Need to wait for clusters to fix
| Development | In progress | Melissa
| Testing | Include % of testing | Harry |  |  | Source file obtained. Testing in progress
| Defect |  |  |  | Suspense acc requirement /data issues
Impersonal accounts | Requirements | RBB - Analysis of accounts | RBB |  |  | In progress by RBB
|  | CIB - results | Minothi |  |  | Additional data to compared to new rules. RBB - CIB accounts (close off with Phakamile)
|  | 3. Wealth - Followed up with Elena as to who will notify GAML of new impersonal accounts | Minothi |  |  | Need confirmation re notification to Group AML. Follow up on Wealth S&I accounts
| Write up (GAML/GL) | 1. An addendum to be added once the requirements are finalised | Minothi
| Mapping | 1. Mappings to be updated when the requirements are finalised | Minothi
Development
Testing
| Defect | 1. Review of current defect list | Entire team
Suspense accounts | Requirements | 1. CPS, MG and ACB RBB suspense accounts to be investigated to indicate whether they would have underlying clients | Shantha |  |  | Shanta to request assistance from MC - Minothi to be included in meeting
| Write up (GAML/GL) | 1. An addendum to be added once the requirements are finalised | Minothi
Mapping
| Development | Development to take place after finalisation of the mapping update | Melissa
Testing
Defect
CMA Bank Statements | Write-up | Update CMA bank statements write up | Minothi |  |  | Completed and with RBB for review
|  | Update of methodology | Group AML |  |  | In register for them to update
China Systems | Mapping | 1. Engaging with China Systems team to understand transactions | Minothi/Tlalane |  |  | Meeting on Friday to complete mappings
| Development | Development for China Systems transactions per mappings | Melissa
| Testing | Regression testing for completed development | TBA
Tracibility matrix | Requirements | Utilise list completed in 2019 to update | Nelene |  |  | Utilise current FIC requirements
Independent testing | Bopcus |  | Peter |  |  | LM to chat to PS re independent testing
| Non reportable |  | Peter
| Bopcard Resident | In progress | Peter |  |  | Script to be finalised and testing to be completed by 14/10
| Bopcard Non-resident |  | Peter
| CMA - ACB | Completed | Peter |  |  | CIM900 access required to finalise
| CMA - CPS | Completed | Peter |  |  | CIM900 access required to finalise
| CMA - Magtape | Completed | Peter |  |  | CIM900 access required to finalise
ROA exceptions - across all reporting categories | All categories | Extract to be run of all NAR clients | Nelene/melissa |  |  | 1.Provide NAR exceptions to clusters 2. Run extract for all NAR clients (deprioritised)
Exceptions management process | All categories | 1. Resolve Finsurv and CMA category financial exceptions process | Nelene |  |  | NS busy with documentation - Finsurv 28/10
|  | 2. Resolve cluster client exceptions process | Nelene |  |  | RBB to finalise where exceptions will flow
Country prefix code | All categories | Current proposed solution will not solve for the issue. Clusters to provide alternative solution | Clusters |  |  | Group AML to resolve through DMO
Solution design | All categories | IER status - IB to update current document and distribute to Group AML and Group Legal | Ilse |  |  | Write up updated and sent to RBB. IER status to be reviewed with RBB for Bopcard
Data lineage | All categories | Confirmation of hand-over to Group AML | Lauretta | Completed |  | Email sent to stakeholders
|  | Analysis hand over to Group AML team | Lauretta | Completed |  | Completed
CIS/MDM migration |  | Testing of exceptions to be completed | Testing team |  |  | Cluster have requested data for this investigtion
GATR exceptions automation |  | Development of GATR exceptions process flow | Eric /Adaptris | 2020-10-28 | Dependent on completion of exceptions process | Adaptrisl IA received. To confirm timing today for update to the plan
Breach process |  | Not at this time | Nelene |  |  | Process has been reviewed and updated. Final review and approval once reporting categories are finalised
Passport/ID no blank |  | Defect to be closed? |  |  |  | ME team to review whether this is a capturing issue. NS to follow up on this. A CVH issue, not ME onboarding. RBB to follow up to close this issue. Testing team to review and close if correct results are obtained
FIU message |  | Group AML has escalated to FIC. Awaiting feedback | Group AML | TBA | FIC | Matter raised with Group AML
Dormant accounts /GL account |  | To be resolved for RBB - escalation to Group AML required | Ilse / Group AML | 2020-11-03 |  | To be managed as part of BAU - hand over meeting 2 Nov 20
Approval of testing by clusters | Testing sign-off by clusters | Complete testing Complete traceability matrix Obtain sign-off | Peter / Testing team
Methodology register | Register of changes required to the methodology | First draft of registrer completed Update as an when required Provide to Group AML for update of methodology document | Lauretta / Group AML | 2020-11-03 |  | Register shared with Group AML. MJ responded that it would be updated once and requested feedback from RBB. To be managed as BAU
Financial reconciliations | 3 way recon for IFTR | Complete hand-over from James Vlok to Group Finance Complete 3 way recon and obtain approval Implement 3 way recon for IFTR | Lachelle van der Merwe / Group Finance / NDW | 2020-11-03 |  | GF - will also be BAU. Preyesh will manage this going forward. CTR first and then IFTR - round out discussion. To be managed as BAU
No | Action Items | Responsible | Feedback/Notes | Next follow up date | Status | Defect No
1 | SWIFT Inflow - Lauretta and Tlalane to engage with Mamello on this | LM/TN | 14/9/2020: 1. TN has updated mappings to include IER status and they do have it on BOPCUS for certain transactions. FINSURV team indicated that we need to include IER for BOPCUS. 2. TL and LB to engage with Mamello by COB 16/9 - LM asked to keep this item open till then 22/9/2020: 1. LM has advised that the mappings were updated and that this item should be closed | Thurs, 17th Sep | Closed
2 | SWIFT Outflow - Meeting with Mamello and FINSURV team
2.1 | SWIFT Outflow - Meeting with Mamello and FINSURV team to be held to discuss this | MC | 14/9/2020: 1. Meeting was held on 8/9 to confirm which account numbers the outgoing team would manage 2. Mamello requested dataand indicated that previous extract would suffice but she then requested Aug data - Minothi to confirm with Mamello as whether a new extract is required 16/9/2020: 1. Mamello confirmed that she wants a new extract for August so that it can be distributed to the team for them to advise on the acocunt numbers 2. See 2.3 below | Refer to 2.3 below | Open
2.2. | Meeting on 8/9: Mamello to send an email pertaining to the descriptions she requires on the exception report | Mamello | Mamello has discussed this with Melissa |  | Closed
2.3 | Meeting on 8/9: 2. Melissa to then run an extract for August 2020 to extract the outgoing FINSURV impersonal and suspense account exceptions (this would include all impersonal accounts and not be limited to the list that the incoming team provided) – the following account numbers need to be excluded as they would only be applicable to domestic transactions: 1565000218, 1565000226, 1565000234, 1565000242 The extract to include the descriptions provided by Mamello. | MC | 22/09/2020: 1. Melissa has run the extrat for the data that is available in NDW 2. Mamello has some queries pertaining to the data range as it is not for the 1st Aug - 31st Aug - Melissa has advised that the GPS data is not available in NDW for that date range 3. MC will respond to Mamello's addtional queries. |  | Open
2.4 | Meeting on 8/9: 3. Melissa to distribute the file to Mamello and the project team | MC |  |  | Open
2.5 | Meeting on 8/9: Mamello to send the file to all stakeholders and Dewald to obtain input. The team will also confirm whether we must send all the impersonal account exceptions to them or whether there is a list of accounts that is specific to the outgoing transactions team - this item will also answer Shantha's query about the MFC account number | Mamello |  |  | Open
2.6 | Mtng on 8/9:Minothi to set up meeting with Suzette Steyn and Linda Botman from Cape Town | MM | 22/09/2020: Meeting scheduled for 22/9/2020 with CT stakeholders to discuss exceptions and account numbers that the CT outgoing exceptions team will handle |  | Open
2.7 | Mtng on 8/9: Nelene to schedule a meeting with stakeholders to discuss the process after the extract has been distributed (Mamello will advise when this may be done after discussion pertaining to volumes with Dewald) | Nelene |  |  | Open
3 | Process required when a new Impersonal account is opened | Suzette/MM/Shantha | 14/9/2020: 1. CIB have given us contact details 2. Lauretta has engaged with Suzette 3. RBB still finalising I&S 16/9/2020: 1. Suzette will advise by COB Friday 2. Minothi to contact Ryan Folster to find out if there can be a process for when new impersonal accounts are opened for any cluster, can they automatically notify GAML. Also ask him whether only GBS will be allowed to open impersonal account numbers for all cluster. Ask him about suspense account numbers as well. 3. Shantha indicated he will advise who will notify GAML of whether the account needs to be considered for IFTR reporting i.e. whether funds could have been transferred to an undelrying account 22/9/2020: 1. Suzette has still not advised - LM to esclate to Elena, Ilse and Surekha 2. MM still needs to engage with Ryna | Fri, 25th Sep | Open
4 | SWIFT Transactions - issues with identifying underlying client's account number from SWIFT message
4.1 | Melissa to send Shantha examples | Melissa | Done |  | Closed
4.2 | Melissa to investigate to see if there is an issue with extra spaces that could be rectified | Melissa | 14/9/2020: Melissa to provide feedback by tomorrow 22/09/2020: 1. Melissa has invetigated and identified an issue which has been resolved and the code has been updated 2. Waiting for a rerun to test this | Mon, 28th Sep | Open
4.3 | Notify Tlalane that Bash advised that the bank's strategy is to move towards automation - She must notify the SWIFT team must work towards rectifying misplaced data on SWIFT message | Minothi | 14/9/2020: 1. MM notified TN 2. Ilse advised that it is very difficult for project to tell SWIFT team what they need to do to get their stuff automated - TN, IB need to bring this to GAML's attention as this is not a project deliverable 3. Item to be kept open until meeting with GAML is held and they take ownership to drive this change 22/09/2020: 1. To be discussed with GAML next Monday | Tues, 29th Sep | Open
5 | RBB to engage with Bradley and Jackie regarding Corporate Saver | Shantha | 14/9/2020: 1. Shantha advised that he will confirm which transactions belong to RBB and which CIB and provide feedback 2. Shantha advised that he met with Corp Saver today and that it will be carried over till next week | Mon, 21st Sep | Open
6 | Process is required when an exception is routed to the business | Nelene |  | Mon, 28th Sep | Open
7 | MFC Impersonal Account transactions
7.1 | Melissa to investigate whether she can identify MFC accounts via product code | Melissa/MM | 14/09/2020: 1. Melissa to provide feedback by COB 16/09/2020: 1. Melissa has provided feedback and Eric has provided feedback that the code is available in NDW 2. The account numbers provided were MFC CA - Minothi to confirm whether this is one of the 12 account numbers provided by the FINSURV team - if yes, FINSURV team would handle the exception and provide underlying client's details (MM still to confirm with regarding to FINSURV Outgoing team about all 12 account numbers) - covered under point 22/09/2020: 1. MM advised that the account number is not one of the 12 that the FINSURV team would be managing 2. MM has contacted Eric as CTR has a solution for identifying underlying clients for impersonal accounts - awaiting criteria from Eric | Fri, 25th Sep | Open
7.2 | Melissa to investigate GPS Out file to see if the underlying client's account number is the file | Melissa | 14/09/2020: 1. Melissa will be sending out an email to Tlalane and team as the GPS out file still contains impersonal accounts - TN and MC to meet to discuss for them to investigate 22/09/2020: 1. Melissa to chat to Tlalane pertaining to engagements with the GPS team to get their input | 1st Oct | Open
8 | Card Settlement/Project transactions
8.1 | Melissa to send Shantha CMA EFT card settlement transactions in order for him to investigate | Melissa | 14/09/2020: 1. Melissa to send one file to cover all suspense and impersonal account transactions for CMS EFT - this will cover item 12.1 2. Melissa advised that CPS and ACB completed - she just needs to engage with Shantha regarding fields he requires 16/9/2020: Shantha received the files this morning - item closed | Tues, 15th Sep | Closed
8.2 | Shantha to engage with the card team to establish which account numbers are used purely for settlement purposes | Shantha | 14/09/2020: 1. Shanta advised to not go with account numbers as there are some account numbers which are used for both settlement and have underlying clients 2. Shantha advised that he is engaging with Card to understand which account numbers are being used purely settlement purposes 3. Ilse advised that Shantha need to engage with Card to understand which card account numbers are being used purely for settlement purposes 4. MM indicated that the card team should be able to provide which settlement accounts are being used purely for settlement and those being used for dual purpose 5. Davin asked to have a focussed call to discuss this - Davin to advise who from CARD to invite and will set up the meeting | Thurs, 17th Sep | Open
9 | GBS transactions - project team to engage with GBS to understand their transactions | Phakamile | 16/09/2020: 1. MM indicated that the GBS team confirmed that it is out of scope as GBS transactions would never have underlying accounts 2. PZ investigated how to identify GBS transactions in NDW - she has referred this to another analyst within NDW 22/09/2020: 1. PZ has provided us with the table name and she will provide us with the field names of the profit code 2. MM send an email to Shantha to ask him about how to identify a transactions profit code | Wed, 23rd Sep | Open | 49
10 | CIB Corp Saver - Minothi to set up session with Shantha, Eric and Melissa to unpack further | Shantha | 16/09/2020: Shantha to have meeting and advise whether RBB and CIB will need to resolve who is owning the transactions as the transaction will be routed to them. | Fri, 18th Sep | Open
11 | Other Cluster transactions - Minothi to investigate | Minothi | 16/09/2020: 1. Wealth: MM to check account numbers against Eric's/Issack's list of impersonal account numbers 2: CIB: Melissa to advise on account category and client type 22/9/2020: 1. Harry to find original email as MM investigations show that the account numbers do belong to Wealth - confirmed against the list provided by Wealth head of finance 2. MC has advised on client type. Engaged with Eric about account category - Eric requested examples from CIB -CIB has sent through the examples. Eric invesigating in NDW . | Fri, 25th Sep | Open
12 | CMA EFT Suspense account transactions
12.1 | Melissa to send Shantha CPS, MG and ACB GL suspense account transactions | Melissa | Closed on 16/9/2020 |  | Closed
12.2 | Shantha will advise with regards to CMA EFT GL settlement transactions that being with a 9 would have an underlying clients | Shantha | 16/9/2020: Shantha advised that this is in progress | TBC | Open
13 | FINSURV Exceptions: Shantha to advise which business areas these impersonal account transactions need to be routed to | Shantha | 16/9/2020: 1. Shantha advised that this item is In progress 2. Ilse advised that the transaction exceptions would be sent via email but in future it will possibly be via.GATR (Shantha asked to confirm with Bash) | TBC | Open
14 | CMA EFT: Shantha to advise which business areas CPS, MG and ACB exceptions need to be routed to | Shantha | 16/9/2020: 1. Shantha advised that this item is In progress 2. Ilse advised that the transaction exceptions would be sent via email but in future it will possibly be via.GATR (Shantha asked to confirm with Bash) | TBC | Open
15 | List of fields on Impersonal account exceptions report
15.1 | Minothi to engage with Melissa to confirm fields on current FIC report | Minothi | 16/9/2020: 1. Minothi indicated that this is in progress 22/9/2020: 1. Melissa and MM have met and this item is in progress | Fri, 25th Sep | Open
15.2 | Minothi to send file that was agreed with the other clusters to Shantha | Minothi | 16/9/2020: 1. Minothi indicated that this is in progress | TBC | Open
15.3 | Shantha to confirm list of fields RBB require with the RBB business areas | Shantha | 16/9/2020 Shantha awaiting file from Minothi | TBC | Open

## 28OCT20 (hidden)
IFTR DSU - 28 October 2020
Reporting Category / Issue | Task | Outstanding task/Progress | Responsibility | Date to complete | Blockers/Escalation | Comments
Bopcus/Non-reportable | Requirements | Requirements N/A
| Write up (GAML/GL) | N/A
| Mapping | FACTS - missing account number | Tlalane | 2020-10-28 |  | FACTS - missing account numbers, BA and Dev to investigate - could be a timing issue - could require rerun of data.
| Development | China Systems / Swift message | Melissa/Tlalane |  | Meeting with Rene on Friday 30/10 | TBA on investigation. Dev will be required for China Systems and for the Swift message (GPS in account numbers)
| Testing | Regression testing for comments node | CIB: Ravi/Lakshmi RBB: Nkateko/Ntsoaki |  | RBB/Wealth testing to be planned and executed | GPS status completed. No issues picked up. Will retest FACTS once resolved. Provide list of test cases to be completed here. Peter to share test cases
| Defect |  | Ntsoaki/ Nkateko | 2020-10-29 |  | Non reportable execution to start today
Bopcard Resident | Requirements | Not applicable
| Write up (GAML/GL) | Not applicable
| Mapping | Not applicable
| Development | Not applicable
| Testing |  |  |  |  | Waiting for completion of other categories / S&I before retesting
Defect
Bopcard Non-resident | Requirements | Requirements N/A |  |  |  | Done
Write up (GAML/GL)
| Mapping | Development | Phakamile/Minothi/Melissa | 2020-10-28 | Access to GBM table | Need table in ODS for country code. Met with TRB to obtain approval for development on ODS. Exceptions file run - impersonal accounts found (2) and NMC - country code (flow out) blank is source - need to find source to look at data field. Impersonal picked up in refreshedat dat. NOT MY CLIENT exceptions picks up
|  | Testing | Harry | 2020-10-28 | CAMS source file | Reviewed fields in data that was received. Finalise with Phakamile and see if the data is sufficient for use
| Development | Country code to derive currency | Melissa |  |  | Waiting for the table to land in ODS
| Testing | Data | Harry | 2020-10-28 | Source file | Reviewed fields in data that was received. Finalise with Phakamile and see if the data is sufficient for use. Source file received LM has prioritised with Elia team. LM to confirm when the file will be sent for testing
| Defect |  |  |  |  | AMEX table to be updated by card. PE to send email to LM and LM to prioritise with Davin
CMA - ACB | Requirements | Requirement N/A
| Write up (GAML/GL) | Write up - | Phakamile/Minothi/Melissa |  |  | Write-up to be completed for 2 issues on ACB. MC to check file that lands in layer 0 to check on date issue (source or NDW issue)
| Mapping | Interbank sequence | Minothi |  |  | This is an industry wide problem - Write up to Group AML on way forward . Done sent yesterday
| Development | Development | Melissa |  |  | Dependent on outcome of Group AML feedback
| Testing | In progress | Nkateko |  |  | 80%. Waiting for suspense&impersonal to complete testing
| Defect | Testing | Minothi | In and out 85% | Suspense acc requirement /data issues | 1. Address /city name also a data misalignment issue. Group AML / FIU. Feedback received from the FIC 16/10. Group AML to discuss directly with the FIC - how do we close this out with Group AML. How to move to BAU?. 2. SWIFT code blank for NOT MY CLIENT3. Denoda access for Peter to verify from source
CMA - CPS | Requirements | Requirements N/A
| Write up (GAML/GL) | Write Up N/a
| Mapping | Mappings | Clusters/NDW
| Development | Development | NDW
| Testing | Testing | Ntsoaki |  |  | 2. Address /city name also a data misalignment issue. Reason field/ FIU. Feedback received from the FIC 16/10. Ifo not quite useful. NDW requested PM to confirm which version of the FIC schema was used to provide feedbck. Testing team to provide Melissa with screen shots and transction numbers. CPS - Swift code loaded as 0 - need data access here (PS) - MC to assist with view of file
| Defect |  |  |  | Suspense acc requirement /data issues | 2 defects to be addressed (covered under suspense and impersonal accounts). Rounding issue with account numbers (meeting with Charl to resolve). Shanta - email 22/10 - look at issue and respond (MC/Nelene). Defect closed | Close defect. Picking up transaction that are not cross boarder. Melissa
CMA - Magtape | Requirements | Requirements N/A
| Write up (GAML/GL) | Not applicable
| Mapping | Address/city name not in CIS - but need to go to exceptions. |  | TBA |  | Need to wait for clusters to fix
| Development | In progress | Melissa
| Testing | Include % of testing | Harry |  | 15% | Source file obtained. Testing in progress but progressing slow. Harry to confirm end date 29/10
| Defect |  |  |  | Suspense acc requirement /data issues
Impersonal accounts | Requirements | RBB - Analysis of accounts | RBB |  |  | In progress by RBB
|  | CIB - results | Minothi |  |  | Additional data to compared to new rules. RBB - CIB accounts (close off with Phakamile)
|  | 3. Wealth - Followed up with Elena as to who will notify GAML of new impersonal accounts | Minothi |  |  | Need confirmation re notification to Group AML. Follow up on Wealth S&I accounts
| Write up (GAML/GL) | 1. An addendum to be added once the requirements are finalised | Minothi
| Mapping | 1. Mappings to be updated when the requirements are finalised | Minothi
Development
Testing
| Defect | 1. Review of current defect list | Entire team
Suspense accounts | Requirements | 1. CPS, MG and ACB RBB suspense accounts to be investigated to indicate whether they would have underlying clients | Shantha |  |  | Shanta to request assistance from MC - Minothi to be included in meeting
| Write up (GAML/GL) | 1. An addendum to be added once the requirements are finalised | Minothi
Mapping
| Development | Development to take place after finalisation of the mapping update | Melissa
Testing
Defect
CMA Bank Statements | Write-up | Update CMA bank statements write up | Minothi |  |  | Completed and with RBB for review
|  | Update of methodology | Group AML |  |  | In register for them to update
China Systems | Mapping | 1. Engaging with China Systems team to understand transactions | Tlalane |  |  | Meeting on Friday to complete mappings
| Development | Development for China Systems transactions per mappings | Melissa
| Testing | Regression testing for completed development | TBA
Tracibility matrix | Requirements | Utilise list completed in 2019 to update | Nelene |  |  | Utilise current FIC requirements
Independent testing | Bopcus |  | Peter |  |  | LM to chat to PS re independent testing
| Non reportable |  | Peter
| Bopcard Resident | In progress | Peter |  |  | Script to be finalised and testing to be completed by 14/10
| Bopcard Non-resident |  | Peter
| CMA - ACB | Completed | Peter |  |  | CIM900 access required to finalise
| CMA - CPS | Completed | Peter |  |  | CIM900 access required to finalise
| CMA - Magtape | Completed | Peter |  |  | CIM900 access required to finalise
ROA exceptions - across all reporting categories | All categories | Extract to be run of all NAR clients | Nelene/melissa |  |  | 1.Provide NAR exceptions to clusters 2. Run extract for all NAR clients (deprioritised)
Exceptions management process | All categories | 1. Resolve Finsurv and CMA category financial exceptions process | Nelene |  |  | NS busy with documentation - Finsurv 28/10 and update a write up to Group AML | Update write to Group AML
|  | 2. Resolve cluster client exceptions process | Nelene |  |  | RBB to finalise where exceptions will flow
Country prefix code | All categories | Current proposed solution will not solve for the issue. Clusters to provide alternative solution | Group AML |  |  | Group AML to resolve through DMO
Solution design | All categories | IER status - IB to update current document and distribute to Group AML and Group Legal | Ilse |  |  | Write up updated and sent to RBB. IER status to be reviewed with RBB for Bopcard
Data lineage | All categories | Confirmation of hand-over to Group AML | Lauretta | Completed |  | Email sent to stakeholders
|  | Analysis hand over to Group AML team | Lauretta | Completed |  | Completed
CIS/MDM migration |  | Testing of exceptions to be completed | Testing team |  |  | Cluster have requested data for this investigtion. Defects retest to confirm if issue persist after migration. Testing to share their final list with LM
GATR exceptions automation |  | Development of GATR exceptions process flow | Eric /Adaptris | 2020-10-28 | Dependent on completion of exceptions process | Adaptrisl IA received. To confirm timing today for update to the plan
Breach process |  | Not at this time | Nelene |  |  | Process has been reviewed and updated. Final review and approval once reporting categories are finalised
Passport/ID no blank |  | Defect to be closed? | Ntsoaki | 2020-10-28 |  | ME team to review whether this is a capturing issue. NS to follow up on this. A CVH issue, not ME onboarding. RBB to follow up to close this issue. Testing team to review and close if correct results are obtained. Ntskoaki to do a retest today
FIU message |  | Group AML has escalated to FIC. Awaiting feedback | Group AML | TBA | FIC | Matter raised with Group AML
Dormant accounts /GL account |  | To be resolved for RBB - escalation to Group AML required | Ilse / Group AML | 2020-11-03 |  | To be managed as part of BAU - hand over meeting 2 Nov 20
Approval of testing by clusters | Testing sign-off by clusters | Complete testing Complete traceability matrix Obtain sign-off | Peter / Testing team
Methodology register | Register of changes required to the methodology | First draft of registrer completed Update as an when required Provide to Group AML for update of methodology document | Lauretta / Group AML | 2020-11-03 |  | Register shared with Group AML. MJ responded that it would be updated once and requested feedback from RBB. To be managed as BAU
Financial reconciliations | 3 way recon for IFTR | Complete hand-over from James Vlok to Group Finance Complete 3 way recon and obtain approval Implement 3 way recon for IFTR | Lachelle van der Merwe / Group Finance / NDW | 2020-11-03 |  | GF - will also be BAU. Preyesh will manage this going forward. CTR first and then IFTR - round out discussion. To be managed as BAU
No | Action Items | Responsible | Feedback/Notes | Next follow up date | Status | Defect No
1 | SWIFT Inflow - Lauretta and Tlalane to engage with Mamello on this | LM/TN | 14/9/2020: 1. TN has updated mappings to include IER status and they do have it on BOPCUS for certain transactions. FINSURV team indicated that we need to include IER for BOPCUS. 2. TL and LB to engage with Mamello by COB 16/9 - LM asked to keep this item open till then 22/9/2020: 1. LM has advised that the mappings were updated and that this item should be closed | Thurs, 17th Sep | Closed
2 | SWIFT Outflow - Meeting with Mamello and FINSURV team
2.1 | SWIFT Outflow - Meeting with Mamello and FINSURV team to be held to discuss this | MC | 14/9/2020: 1. Meeting was held on 8/9 to confirm which account numbers the outgoing team would manage 2. Mamello requested dataand indicated that previous extract would suffice but she then requested Aug data - Minothi to confirm with Mamello as whether a new extract is required 16/9/2020: 1. Mamello confirmed that she wants a new extract for August so that it can be distributed to the team for them to advise on the acocunt numbers 2. See 2.3 below | Refer to 2.3 below | Open
2.2. | Meeting on 8/9: Mamello to send an email pertaining to the descriptions she requires on the exception report | Mamello | Mamello has discussed this with Melissa |  | Closed
2.3 | Meeting on 8/9: 2. Melissa to then run an extract for August 2020 to extract the outgoing FINSURV impersonal and suspense account exceptions (this would include all impersonal accounts and not be limited to the list that the incoming team provided) – the following account numbers need to be excluded as they would only be applicable to domestic transactions: 1565000218, 1565000226, 1565000234, 1565000242 The extract to include the descriptions provided by Mamello. | MC | 22/09/2020: 1. Melissa has run the extrat for the data that is available in NDW 2. Mamello has some queries pertaining to the data range as it is not for the 1st Aug - 31st Aug - Melissa has advised that the GPS data is not available in NDW for that date range 3. MC will respond to Mamello's addtional queries. |  | Open
2.4 | Meeting on 8/9: 3. Melissa to distribute the file to Mamello and the project team | MC |  |  | Open
2.5 | Meeting on 8/9: Mamello to send the file to all stakeholders and Dewald to obtain input. The team will also confirm whether we must send all the impersonal account exceptions to them or whether there is a list of accounts that is specific to the outgoing transactions team - this item will also answer Shantha's query about the MFC account number | Mamello |  |  | Open
2.6 | Mtng on 8/9:Minothi to set up meeting with Suzette Steyn and Linda Botman from Cape Town | MM | 22/09/2020: Meeting scheduled for 22/9/2020 with CT stakeholders to discuss exceptions and account numbers that the CT outgoing exceptions team will handle |  | Open
2.7 | Mtng on 8/9: Nelene to schedule a meeting with stakeholders to discuss the process after the extract has been distributed (Mamello will advise when this may be done after discussion pertaining to volumes with Dewald) | Nelene |  |  | Open
3 | Process required when a new Impersonal account is opened | Suzette/MM/Shantha | 14/9/2020: 1. CIB have given us contact details 2. Lauretta has engaged with Suzette 3. RBB still finalising I&S 16/9/2020: 1. Suzette will advise by COB Friday 2. Minothi to contact Ryan Folster to find out if there can be a process for when new impersonal accounts are opened for any cluster, can they automatically notify GAML. Also ask him whether only GBS will be allowed to open impersonal account numbers for all cluster. Ask him about suspense account numbers as well. 3. Shantha indicated he will advise who will notify GAML of whether the account needs to be considered for IFTR reporting i.e. whether funds could have been transferred to an undelrying account 22/9/2020: 1. Suzette has still not advised - LM to esclate to Elena, Ilse and Surekha 2. MM still needs to engage with Ryna | Fri, 25th Sep | Open
4 | SWIFT Transactions - issues with identifying underlying client's account number from SWIFT message
4.1 | Melissa to send Shantha examples | Melissa | Done |  | Closed
4.2 | Melissa to investigate to see if there is an issue with extra spaces that could be rectified | Melissa | 14/9/2020: Melissa to provide feedback by tomorrow 22/09/2020: 1. Melissa has invetigated and identified an issue which has been resolved and the code has been updated 2. Waiting for a rerun to test this | Mon, 28th Sep | Open
4.3 | Notify Tlalane that Bash advised that the bank's strategy is to move towards automation - She must notify the SWIFT team must work towards rectifying misplaced data on SWIFT message | Minothi | 14/9/2020: 1. MM notified TN 2. Ilse advised that it is very difficult for project to tell SWIFT team what they need to do to get their stuff automated - TN, IB need to bring this to GAML's attention as this is not a project deliverable 3. Item to be kept open until meeting with GAML is held and they take ownership to drive this change 22/09/2020: 1. To be discussed with GAML next Monday | Tues, 29th Sep | Open
5 | RBB to engage with Bradley and Jackie regarding Corporate Saver | Shantha | 14/9/2020: 1. Shantha advised that he will confirm which transactions belong to RBB and which CIB and provide feedback 2. Shantha advised that he met with Corp Saver today and that it will be carried over till next week | Mon, 21st Sep | Open
6 | Process is required when an exception is routed to the business | Nelene |  | Mon, 28th Sep | Open
7 | MFC Impersonal Account transactions
7.1 | Melissa to investigate whether she can identify MFC accounts via product code | Melissa/MM | 14/09/2020: 1. Melissa to provide feedback by COB 16/09/2020: 1. Melissa has provided feedback and Eric has provided feedback that the code is available in NDW 2. The account numbers provided were MFC CA - Minothi to confirm whether this is one of the 12 account numbers provided by the FINSURV team - if yes, FINSURV team would handle the exception and provide underlying client's details (MM still to confirm with regarding to FINSURV Outgoing team about all 12 account numbers) - covered under point 22/09/2020: 1. MM advised that the account number is not one of the 12 that the FINSURV team would be managing 2. MM has contacted Eric as CTR has a solution for identifying underlying clients for impersonal accounts - awaiting criteria from Eric | Fri, 25th Sep | Open
7.2 | Melissa to investigate GPS Out file to see if the underlying client's account number is the file | Melissa | 14/09/2020: 1. Melissa will be sending out an email to Tlalane and team as the GPS out file still contains impersonal accounts - TN and MC to meet to discuss for them to investigate 22/09/2020: 1. Melissa to chat to Tlalane pertaining to engagements with the GPS team to get their input | 1st Oct | Open
8 | Card Settlement/Project transactions
8.1 | Melissa to send Shantha CMA EFT card settlement transactions in order for him to investigate | Melissa | 14/09/2020: 1. Melissa to send one file to cover all suspense and impersonal account transactions for CMS EFT - this will cover item 12.1 2. Melissa advised that CPS and ACB completed - she just needs to engage with Shantha regarding fields he requires 16/9/2020: Shantha received the files this morning - item closed | Tues, 15th Sep | Closed
8.2 | Shantha to engage with the card team to establish which account numbers are used purely for settlement purposes | Shantha | 14/09/2020: 1. Shanta advised to not go with account numbers as there are some account numbers which are used for both settlement and have underlying clients 2. Shantha advised that he is engaging with Card to understand which account numbers are being used purely settlement purposes 3. Ilse advised that Shantha need to engage with Card to understand which card account numbers are being used purely for settlement purposes 4. MM indicated that the card team should be able to provide which settlement accounts are being used purely for settlement and those being used for dual purpose 5. Davin asked to have a focussed call to discuss this - Davin to advise who from CARD to invite and will set up the meeting | Thurs, 17th Sep | Open
9 | GBS transactions - project team to engage with GBS to understand their transactions | Phakamile | 16/09/2020: 1. MM indicated that the GBS team confirmed that it is out of scope as GBS transactions would never have underlying accounts 2. PZ investigated how to identify GBS transactions in NDW - she has referred this to another analyst within NDW 22/09/2020: 1. PZ has provided us with the table name and she will provide us with the field names of the profit code 2. MM send an email to Shantha to ask him about how to identify a transactions profit code | Wed, 23rd Sep | Open | 49
10 | CIB Corp Saver - Minothi to set up session with Shantha, Eric and Melissa to unpack further | Shantha | 16/09/2020: Shantha to have meeting and advise whether RBB and CIB will need to resolve who is owning the transactions as the transaction will be routed to them. | Fri, 18th Sep | Open
11 | Other Cluster transactions - Minothi to investigate | Minothi | 16/09/2020: 1. Wealth: MM to check account numbers against Eric's/Issack's list of impersonal account numbers 2: CIB: Melissa to advise on account category and client type 22/9/2020: 1. Harry to find original email as MM investigations show that the account numbers do belong to Wealth - confirmed against the list provided by Wealth head of finance 2. MC has advised on client type. Engaged with Eric about account category - Eric requested examples from CIB -CIB has sent through the examples. Eric invesigating in NDW . | Fri, 25th Sep | Open
12 | CMA EFT Suspense account transactions
12.1 | Melissa to send Shantha CPS, MG and ACB GL suspense account transactions | Melissa | Closed on 16/9/2020 |  | Closed
12.2 | Shantha will advise with regards to CMA EFT GL settlement transactions that being with a 9 would have an underlying clients | Shantha | 16/9/2020: Shantha advised that this is in progress | TBC | Open
13 | FINSURV Exceptions: Shantha to advise which business areas these impersonal account transactions need to be routed to | Shantha | 16/9/2020: 1. Shantha advised that this item is In progress 2. Ilse advised that the transaction exceptions would be sent via email but in future it will possibly be via.GATR (Shantha asked to confirm with Bash) | TBC | Open
14 | CMA EFT: Shantha to advise which business areas CPS, MG and ACB exceptions need to be routed to | Shantha | 16/9/2020: 1. Shantha advised that this item is In progress 2. Ilse advised that the transaction exceptions would be sent via email but in future it will possibly be via.GATR (Shantha asked to confirm with Bash) | TBC | Open
15 | List of fields on Impersonal account exceptions report
15.1 | Minothi to engage with Melissa to confirm fields on current FIC report | Minothi | 16/9/2020: 1. Minothi indicated that this is in progress 22/9/2020: 1. Melissa and MM have met and this item is in progress | Fri, 25th Sep | Open
15.2 | Minothi to send file that was agreed with the other clusters to Shantha | Minothi | 16/9/2020: 1. Minothi indicated that this is in progress | TBC | Open
15.3 | Shantha to confirm list of fields RBB require with the RBB business areas | Shantha | 16/9/2020 Shantha awaiting file from Minothi | TBC | Open

## 29OCT20 (hidden)
IFTR DSU - 28 October 2020
Reporting Category / Issue | Task | Outstanding task/Progress | Responsibility | Date to complete | Blockers/Escalation | Comments
Bopcus/Non-reportable | Requirements | Requirements N/A
| Write up (GAML/GL) | N/A
| Mapping | FACTS - missing account number | Tlalane | 2020-10-28 |  | FACTS - missing account numbers, BA and Dev to investigate - could be a timing issue - could require rerun of data. | Mamello with middle office today. Feedback due tommorow 30/10
| Development | China Systems / Swift message | Melissa/Tlalane |  | Meeting with Rene on Friday 30/10 | TBA on investigation. Dev will be required for China Systems and for the Swift message (GPS in account numbers)
| Testing | Regression testing for comments node | CIB: Ravi/Lakshmi RBB: Nkateko/Ntsoaki |  | RBB/Wealth testing to be planned and executed | GPS status completed. No issues picked up. Will retest FACTS once resolved. Provide list of test cases to be completed here. Peter to share test cases
| Defect |  | Ntsoaki/ Nkateko | 2020-10-29 |  | Non reportable execution to start today
Bopcard Resident | Requirements | Not applicable
| Write up (GAML/GL) | Not applicable
| Mapping | Not applicable
| Development | Not applicable
| Testing |  |  |  |  | Waiting for completion of other categories / S&I before retesting
Defect
Bopcard Non-resident | Requirements | Requirements N/A |  |  |  | Done
Write up (GAML/GL)
| Mapping | Development | Phakamile/Minothi/Melissa | 2020-10-28 | Access to GBM table | Need table in ODS for country code. Met with TRB to obtain approval for development on ODS. Exceptions file run - impersonal accounts found (2) and NMC - country code (flow out) blank is source - need to find source to look at data field. Impersonal picked up in refreshedat dat. NOT MY CLIENT exceptions picks up
|  | Testing | Harry | 2020-10-28 | CAMS source file | Reviewed fields in data that was received. Finalise with Phakamile and see if the data is sufficient for use
| Development | Country code to derive currency | Melissa |  |  | Waiting for the table to land in ODS
| Testing | Data | Harry | 2020-10-28 | Source file | Reviewed fields in data that was received. Finalise with Phakamile and see if the data is sufficient for use. Source file received LM has prioritised with Elia team. LM to confirm when the file will be sent for testing
| Defect |  |  | 2020-10-30 |  | AMEX table to be updated by card. PE to send email to LM and LM to prioritise with Davin
CMA - ACB | Requirements | Requirement N/A
| Write up (GAML/GL) | Write up - | Phakamile/Minothi/Melissa |  |  | Write-up to be completed for 2 issues on ACB. MC to check file that lands in layer 0 to check on date issue (source or NDW issue) | Exc
| Mapping | Interbank sequence | Minothi |  |  | This is an industry wide problem - Write up to Group AML on way forward . Done sent yesterday
| Development | Development | Melissa |  |  | Dependent on outcome of Group AML feedback
| Testing | In progress | Nkateko |  |  | 80%. Waiting for suspense&impersonal to complete testing
| Defect | Testing | Minothi | In and out 85% | Suspense acc requirement /data issues | 1. Address /city name also a data misalignment issue. Group AML / FIU. Feedback received from the FIC 16/10. Group AML to discuss directly with the FIC - how do we close this out with Group AML. How to move to BAU?. 2. SWIFT code blank for NOT MY CLIENT3. Denoda access for Peter to verify from source | CIM90
CMA - CPS | Requirements | Requirements N/A
| Write up (GAML/GL) | Write Up N/a
| Mapping | Mappings | Clusters/NDW
| Development | Development | NDW
| Testing | Testing | Ntsoaki |  |  | 2. Address /city name also a data misalignment issue. Reason field/ FIU. Feedback received from the FIC 16/10. Ifo not quite useful. NDW requested PM to confirm which version of the FIC schema was used to provide feedbck. Testing team to provide Melissa with screen shots and transction numbers. CPS - Swift code loaded as 0 - need data access here (PS) - MC to assist with view of file | Pendinding verifcation from source by testing team. Denoda access pending
| Defect |  |  |  | Suspense acc requirement /data issues | 2 defects to be addressed (covered under suspense and impersonal accounts). Rounding issue with account numbers (meeting with Charl to resolve). Shanta - email 22/10 - look at issue and respond (MC/Nelene). Defect closed | Close defect. Picking up transaction that are not cross boarder. Melissa
CMA - Magtape | Requirements | Requirements N/A
| Write up (GAML/GL) | Not applicable
| Mapping | Address/city name not in CIS - but need to go to exceptions. |  | TBA |  | Need to wait for clusters to fix
| Development | In progress | Melissa
| Testing | Include % of testing | Harry |  | 15% | Source file obtained. Testing in progress but progressing slow. Harry to confirm end date 29/10
| Defect |  |  | 2020-03-10 | Suspense acc requirement /data issues
Impersonal accounts | Requirements | RBB - Analysis of accounts | RBB |  |  | In progress by RBB
|  | CIB - results | Minothi |  |  | Additional data to compared to new rules. RBB - CIB accounts (close off with Phakamile)
|  | 3. Wealth - Followed up with Elena as to who will notify GAML of new impersonal accounts | Minothi |  |  | Need confirmation re notification to Group AML. Follow up on Wealth S&I accounts
| Write up (GAML/GL) | 1. An addendum to be added once the requirements are finalised | Minothi
| Mapping | 1. Mappings to be updated when the requirements are finalised | Minothi
Development
Testing
| Defect | 1. Review of current defect list | Entire team
Suspense accounts | Requirements | 1. CPS, MG and ACB RBB suspense accounts to be investigated to indicate whether they would have underlying clients | Shantha |  |  | Shanta to request assistance from MC - Minothi to be included in meeting
| Write up (GAML/GL) | 1. An addendum to be added once the requirements are finalised | Minothi
Mapping
| Development | Development to take place after finalisation of the mapping update | Melissa
Testing
Defect
CMA Bank Statements | Write-up | Update CMA bank statements write up | Minothi |  |  | Completed and with RBB for review
|  | Update of methodology | Group AML |  |  | In register for them to update
China Systems | Mapping | 1. Engaging with China Systems team to understand transactions | Tlalane |  |  | Meeting on Friday to complete mappings
| Development | Development for China Systems transactions per mappings | Melissa
| Testing | Regression testing for completed development | TBA
Tracibility matrix | Requirements | Utilise list completed in 2019 to update | Nelene |  |  | Utilise current FIC requirements
Independent testing | Bopcus |  | Peter |  |  | LM to chat to PS re independent testing
| Non reportable |  | Peter
| Bopcard Resident | In progress | Peter |  |  | Script to be finalised and testing to be completed by 14/10
| Bopcard Non-resident |  | Peter
| CMA - ACB | Completed | Peter |  |  | CIM900 access required to finalise
| CMA - CPS | Completed | Peter |  |  | CIM900 access required to finalise
| CMA - Magtape | Completed | Peter |  |  | CIM900 access required to finalise
ROA exceptions - across all reporting categories | All categories | Extract to be run of all NAR clients | Nelene/melissa |  |  | 1.Provide NAR exceptions to clusters 2. Run extract for all NAR clients (deprioritised)
Exceptions management process | All categories | 1. Resolve Finsurv and CMA category financial exceptions process | Nelene |  |  | NS busy with documentation - Finsurv 28/10 and update a write up to Group AML | Update write to Group AML
|  | 2. Resolve cluster client exceptions process | Nelene |  |  | RBB to finalise where exceptions will flow
Country prefix code | All categories | Current proposed solution will not solve for the issue. Clusters to provide alternative solution | Group AML |  |  | Group AML to resolve through DMO
Solution design | All categories | IER status - IB to update current document and distribute to Group AML and Group Legal | Ilse |  |  | Write up updated and sent to RBB. IER status to be reviewed with RBB for Bopcard
Data lineage | All categories | Confirmation of hand-over to Group AML | Lauretta | Completed |  | Email sent to stakeholders
|  | Analysis hand over to Group AML team | Lauretta | Completed |  | Completed
CIS/MDM migration |  | Testing of exceptions to be completed | Testing team |  |  | Cluster have requested data for this investigtion. Defects retest to confirm if issue persist after migration. Testing to share their final list with LM
GATR exceptions automation |  | Development of GATR exceptions process flow | Eric /Adaptris | 2020-10-28 | Dependent on completion of exceptions process | Adaptrisl IA received. To confirm timing today for update to the plan
Breach process |  | Not at this time | Nelene |  |  | Process has been reviewed and updated. Final review and approval once reporting categories are finalised
Passport/ID no blank |  | Defect to be closed? | Ntsoaki | 2020-10-28 |  | ME team to review whether this is a capturing issue. NS to follow up on this. A CVH issue, not ME onboarding. RBB to follow up to close this issue. Testing team to review and close if correct results are obtained. Ntskoaki to do a retest today | Closed
FIU message |  | Group AML has escalated to FIC. Awaiting feedback | Group AML | TBA | FIC | Matter raised with Group AML
Dormant accounts /GL account |  | To be resolved for RBB - escalation to Group AML required | Ilse / Group AML | 2020-11-03 |  | To be managed as part of BAU - hand over meeting 2 Nov 20
Approval of testing by clusters | Testing sign-off by clusters | Complete testing Complete traceability matrix Obtain sign-off | Peter / Testing team
Methodology register | Register of changes required to the methodology | First draft of registrer completed Update as an when required Provide to Group AML for update of methodology document | Lauretta / Group AML | 2020-11-03 |  | Register shared with Group AML. MJ responded that it would be updated once and requested feedback from RBB. To be managed as BAU
Financial reconciliations | 3 way recon for IFTR | Complete hand-over from James Vlok to Group Finance Complete 3 way recon and obtain approval Implement 3 way recon for IFTR | Lachelle van der Merwe / Group Finance / NDW | 2020-11-03 |  | GF - will also be BAU. Preyesh will manage this going forward. CTR first and then IFTR - round out discussion. To be managed as BAU
No | Action Items | Responsible | Feedback/Notes | Next follow up date | Status | Defect No
1 | SWIFT Inflow - Lauretta and Tlalane to engage with Mamello on this | LM/TN | 14/9/2020: 1. TN has updated mappings to include IER status and they do have it on BOPCUS for certain transactions. FINSURV team indicated that we need to include IER for BOPCUS. 2. TL and LB to engage with Mamello by COB 16/9 - LM asked to keep this item open till then 22/9/2020: 1. LM has advised that the mappings were updated and that this item should be closed | Thurs, 17th Sep | Closed
2 | SWIFT Outflow - Meeting with Mamello and FINSURV team
2.1 | SWIFT Outflow - Meeting with Mamello and FINSURV team to be held to discuss this | MC | 14/9/2020: 1. Meeting was held on 8/9 to confirm which account numbers the outgoing team would manage 2. Mamello requested dataand indicated that previous extract would suffice but she then requested Aug data - Minothi to confirm with Mamello as whether a new extract is required 16/9/2020: 1. Mamello confirmed that she wants a new extract for August so that it can be distributed to the team for them to advise on the acocunt numbers 2. See 2.3 below | Refer to 2.3 below | Open
2.2. | Meeting on 8/9: Mamello to send an email pertaining to the descriptions she requires on the exception report | Mamello | Mamello has discussed this with Melissa |  | Closed
2.3 | Meeting on 8/9: 2. Melissa to then run an extract for August 2020 to extract the outgoing FINSURV impersonal and suspense account exceptions (this would include all impersonal accounts and not be limited to the list that the incoming team provided) – the following account numbers need to be excluded as they would only be applicable to domestic transactions: 1565000218, 1565000226, 1565000234, 1565000242 The extract to include the descriptions provided by Mamello. | MC | 22/09/2020: 1. Melissa has run the extrat for the data that is available in NDW 2. Mamello has some queries pertaining to the data range as it is not for the 1st Aug - 31st Aug - Melissa has advised that the GPS data is not available in NDW for that date range 3. MC will respond to Mamello's addtional queries. |  | Open
2.4 | Meeting on 8/9: 3. Melissa to distribute the file to Mamello and the project team | MC |  |  | Open
2.5 | Meeting on 8/9: Mamello to send the file to all stakeholders and Dewald to obtain input. The team will also confirm whether we must send all the impersonal account exceptions to them or whether there is a list of accounts that is specific to the outgoing transactions team - this item will also answer Shantha's query about the MFC account number | Mamello |  |  | Open
2.6 | Mtng on 8/9:Minothi to set up meeting with Suzette Steyn and Linda Botman from Cape Town | MM | 22/09/2020: Meeting scheduled for 22/9/2020 with CT stakeholders to discuss exceptions and account numbers that the CT outgoing exceptions team will handle |  | Open
2.7 | Mtng on 8/9: Nelene to schedule a meeting with stakeholders to discuss the process after the extract has been distributed (Mamello will advise when this may be done after discussion pertaining to volumes with Dewald) | Nelene |  |  | Open
3 | Process required when a new Impersonal account is opened | Suzette/MM/Shantha | 14/9/2020: 1. CIB have given us contact details 2. Lauretta has engaged with Suzette 3. RBB still finalising I&S 16/9/2020: 1. Suzette will advise by COB Friday 2. Minothi to contact Ryan Folster to find out if there can be a process for when new impersonal accounts are opened for any cluster, can they automatically notify GAML. Also ask him whether only GBS will be allowed to open impersonal account numbers for all cluster. Ask him about suspense account numbers as well. 3. Shantha indicated he will advise who will notify GAML of whether the account needs to be considered for IFTR reporting i.e. whether funds could have been transferred to an undelrying account 22/9/2020: 1. Suzette has still not advised - LM to esclate to Elena, Ilse and Surekha 2. MM still needs to engage with Ryna | Fri, 25th Sep | Open
4 | SWIFT Transactions - issues with identifying underlying client's account number from SWIFT message
4.1 | Melissa to send Shantha examples | Melissa | Done |  | Closed
4.2 | Melissa to investigate to see if there is an issue with extra spaces that could be rectified | Melissa | 14/9/2020: Melissa to provide feedback by tomorrow 22/09/2020: 1. Melissa has invetigated and identified an issue which has been resolved and the code has been updated 2. Waiting for a rerun to test this | Mon, 28th Sep | Open
4.3 | Notify Tlalane that Bash advised that the bank's strategy is to move towards automation - She must notify the SWIFT team must work towards rectifying misplaced data on SWIFT message | Minothi | 14/9/2020: 1. MM notified TN 2. Ilse advised that it is very difficult for project to tell SWIFT team what they need to do to get their stuff automated - TN, IB need to bring this to GAML's attention as this is not a project deliverable 3. Item to be kept open until meeting with GAML is held and they take ownership to drive this change 22/09/2020: 1. To be discussed with GAML next Monday | Tues, 29th Sep | Open
5 | RBB to engage with Bradley and Jackie regarding Corporate Saver | Shantha | 14/9/2020: 1. Shantha advised that he will confirm which transactions belong to RBB and which CIB and provide feedback 2. Shantha advised that he met with Corp Saver today and that it will be carried over till next week | Mon, 21st Sep | Open
6 | Process is required when an exception is routed to the business | Nelene |  | Mon, 28th Sep | Open
7 | MFC Impersonal Account transactions
7.1 | Melissa to investigate whether she can identify MFC accounts via product code | Melissa/MM | 14/09/2020: 1. Melissa to provide feedback by COB 16/09/2020: 1. Melissa has provided feedback and Eric has provided feedback that the code is available in NDW 2. The account numbers provided were MFC CA - Minothi to confirm whether this is one of the 12 account numbers provided by the FINSURV team - if yes, FINSURV team would handle the exception and provide underlying client's details (MM still to confirm with regarding to FINSURV Outgoing team about all 12 account numbers) - covered under point 22/09/2020: 1. MM advised that the account number is not one of the 12 that the FINSURV team would be managing 2. MM has contacted Eric as CTR has a solution for identifying underlying clients for impersonal accounts - awaiting criteria from Eric | Fri, 25th Sep | Open
7.2 | Melissa to investigate GPS Out file to see if the underlying client's account number is the file | Melissa | 14/09/2020: 1. Melissa will be sending out an email to Tlalane and team as the GPS out file still contains impersonal accounts - TN and MC to meet to discuss for them to investigate 22/09/2020: 1. Melissa to chat to Tlalane pertaining to engagements with the GPS team to get their input | 1st Oct | Open
8 | Card Settlement/Project transactions
8.1 | Melissa to send Shantha CMA EFT card settlement transactions in order for him to investigate | Melissa | 14/09/2020: 1. Melissa to send one file to cover all suspense and impersonal account transactions for CMS EFT - this will cover item 12.1 2. Melissa advised that CPS and ACB completed - she just needs to engage with Shantha regarding fields he requires 16/9/2020: Shantha received the files this morning - item closed | Tues, 15th Sep | Closed
8.2 | Shantha to engage with the card team to establish which account numbers are used purely for settlement purposes | Shantha | 14/09/2020: 1. Shanta advised to not go with account numbers as there are some account numbers which are used for both settlement and have underlying clients 2. Shantha advised that he is engaging with Card to understand which account numbers are being used purely settlement purposes 3. Ilse advised that Shantha need to engage with Card to understand which card account numbers are being used purely for settlement purposes 4. MM indicated that the card team should be able to provide which settlement accounts are being used purely for settlement and those being used for dual purpose 5. Davin asked to have a focussed call to discuss this - Davin to advise who from CARD to invite and will set up the meeting | Thurs, 17th Sep | Open
9 | GBS transactions - project team to engage with GBS to understand their transactions | Phakamile | 16/09/2020: 1. MM indicated that the GBS team confirmed that it is out of scope as GBS transactions would never have underlying accounts 2. PZ investigated how to identify GBS transactions in NDW - she has referred this to another analyst within NDW 22/09/2020: 1. PZ has provided us with the table name and she will provide us with the field names of the profit code 2. MM send an email to Shantha to ask him about how to identify a transactions profit code | Wed, 23rd Sep | Open | 49
10 | CIB Corp Saver - Minothi to set up session with Shantha, Eric and Melissa to unpack further | Shantha | 16/09/2020: Shantha to have meeting and advise whether RBB and CIB will need to resolve who is owning the transactions as the transaction will be routed to them. | Fri, 18th Sep | Open
11 | Other Cluster transactions - Minothi to investigate | Minothi | 16/09/2020: 1. Wealth: MM to check account numbers against Eric's/Issack's list of impersonal account numbers 2: CIB: Melissa to advise on account category and client type 22/9/2020: 1. Harry to find original email as MM investigations show that the account numbers do belong to Wealth - confirmed against the list provided by Wealth head of finance 2. MC has advised on client type. Engaged with Eric about account category - Eric requested examples from CIB -CIB has sent through the examples. Eric invesigating in NDW . | Fri, 25th Sep | Open
12 | CMA EFT Suspense account transactions
12.1 | Melissa to send Shantha CPS, MG and ACB GL suspense account transactions | Melissa | Closed on 16/9/2020 |  | Closed
12.2 | Shantha will advise with regards to CMA EFT GL settlement transactions that being with a 9 would have an underlying clients | Shantha | 16/9/2020: Shantha advised that this is in progress | TBC | Open
13 | FINSURV Exceptions: Shantha to advise which business areas these impersonal account transactions need to be routed to | Shantha | 16/9/2020: 1. Shantha advised that this item is In progress 2. Ilse advised that the transaction exceptions would be sent via email but in future it will possibly be via.GATR (Shantha asked to confirm with Bash) | TBC | Open
14 | CMA EFT: Shantha to advise which business areas CPS, MG and ACB exceptions need to be routed to | Shantha | 16/9/2020: 1. Shantha advised that this item is In progress 2. Ilse advised that the transaction exceptions would be sent via email but in future it will possibly be via.GATR (Shantha asked to confirm with Bash) | TBC | Open
15 | List of fields on Impersonal account exceptions report
15.1 | Minothi to engage with Melissa to confirm fields on current FIC report | Minothi | 16/9/2020: 1. Minothi indicated that this is in progress 22/9/2020: 1. Melissa and MM have met and this item is in progress | Fri, 25th Sep | Open
15.2 | Minothi to send file that was agreed with the other clusters to Shantha | Minothi | 16/9/2020: 1. Minothi indicated that this is in progress | TBC | Open
15.3 | Shantha to confirm list of fields RBB require with the RBB business areas | Shantha | 16/9/2020 Shantha awaiting file from Minothi | TBC | Open

## 05Nov20202
IFTR DSU - 19 November 2020
Reporting Category / Issue | Task | Outstanding task/Progress | Responsibility | Date to complete | Blockers/Escalation | Comments
Bopcus/Non-reportable | Requirements | Requirements N/A
| Write up (GAML/GL) | N/A
| Mapping | FACTS - missing account number | Tlalane/Mamello | 2020-11-04 | refreshed test data | FACTS - missing account numbers. Feedback received this looks like a timing issue. Updated Test data shared for retest. Issue still persists on NonReportables_Out. Refreshing data. Tlalane to meet with Melissa once shes up an running with her laptop QA tables are planned completion EOD tomorrow anf Prod next Friday.China systems tables to be in QA by EOD 16/11.Herril to follow up with Juan on china system tables. Facts missing numbers, Project team awaiting China systems team to land the tables | 19/11: China Systems: Herril dealing and escalated up. Pat has gotten involved and engaging IBM to deal this issue around China Systems | 20/11 Phakamile confirmed the China systems team are trying to reducethe tables and only onboard the IFTR Tables. Some have been done 2 more tables to go. Commitment to have them committed by EOD
| Development | China Systems / Swift message | Rene | 2020-11-03 |  | Pending Dev 1. Suspense Acc 2. China Systems. Completed Dev 1. ( Rands and cents ) developments completed on Friday. Issue still persists after retest. Issue seems dependant mutilfunded. No issues raised on Inward only Outward its not adding up the foregn amount. Shanta and the testing to confirm to test and cofirm the Inward leg. Feedback shared project to analyse feedback | 19/11: Retest on Local Amount Issue: Tlalane leading the investigation. Ravi also analysing and to confirm | 20/11 Local amount issue to be concluded by EOD (Ravi)
| Testing | Regression testing for comments node | CIB: Ravi/Lakshmi RBB: Nkateko/Ntsoaki |  | 2020-11-04 | Completed testing. CIB and Wealth suspense acc rules..Non Reportable done. Bopcus to be finalizing Bopcus 16/11.Non Reportable and Bopcus testing is concluded ppending SI and amounts and cents defect. SI testing only started 18/11
| Defect |  | Ntsoaki/ Nkateko | 2020-10-29 | No blockers currently | Non reportable execution to started 02/11
Amount(Rands & Cents) is tested and still an issue. Sent to NDW>>Appears related to Multifunded transactions. Tlalane and Nelene engaging around this. Team to meet with Melissa
Bopcard Resident | Requirements | Not applicable
| Write up (GAML/GL) | Not applicable
| Mapping | Not applicable | RBB -Shanta | 2020-11-06 | Awaiting mapping rules from RBB | Pending Mappings - Suspense acc Rules for mapping to be shared by 12pm - 06/11 for review. RBB Rules set given >> Minothi currently busy working on Mappings Wealth Cluster need to send requirements through to NDW
| Development | Not applicable |  |  |  | Pending Dev- Suspense acc and currency code.
| Testing |  |  |  |  | Waiting for completion of other categories / S&I before retesting
| Defect |  |  |  | Supense acc requirement | Testing concluded. Outstanding Test is suspense acc requirements | DEV COMPLETED | 20/11 SI Development in progress. Data extracts will be shared by EOD
Bopcard Non-resident | Requirements | Requirements N/A |  |  |  | Done
Write up (GAML/GL)
Mapping
|  | Currecy code | Minothi | 2020-11-15 | Awaiting card to land the tables | Finalise mappings - Mappings to be completed |  | 20/11 Tlalane has shared currency code mappings
| Development | Country code to derive currency | Card | 2020-11-11 |  | Pending Dev -Suspence acc and curreny code Dev. Sequence number sent to Quinton to prioritise the Dev solution with Bank serv. Currency code commitment to resolve the missing columns by EOD. Mpho and Deon allocated for the day to resolve. Currrecy code tables landed in ODS mapping to start 18/11. - Mapping documnet to be finalised by Tlalane and Phakamile
| Testing | Data | Harry | 2020-10-30 | Source file | Testing starting on the Inwardleg to be finalised 18/11 . Outward leg delayed because of currency code issue. Outward leg to be finalised EOD 18/11 |  | 2020/11/20 Outward leg testing to be finalised 20/11 while NDW concludes Inwards leg with currency code
| Defect |  | Herril | 2020-11-09 | 2020-06-11 | AMEX table to be updated by card. Meeting concluded with RBB and card. Phakamile to confirm the source of the data. . Source confirmed by Phakamile. Herril to advise Need to get syncing to Prod tables done. Herril following up on this. IM logged to land the one Bin list. AMEX issue Nelene to discuss with Melissa and the one Bin List developer assigned to work on it.Minothi to do mappings for comments fields which will also resolve the internal Ref. PM, Nelene and Nico , Minothi to unpack teams feedback | 19/11: Issue on Bin numbers: Nico cannot assist. Card cannot assist. Ilse contacting Hennie Jooste around this | 20/11/2020 Ilse to prioritise with Hennie and provide feedback on way forward
CMA - ACB | Requirements | Requirement N/A
| Write up (GAML/GL) | Write up - | Melissa |  | Write done and sent to Group AML | Write-up to be completed for 2 issues on ACB. MC to check file that lands in layer 0 to check on date issue (source or NDW issue) Issues related to reversals; discussions were held with GAML. Pending GAML | 19/11: GAML need to give feedback around using Not obtained. Surekha to feedback by eod
| Mapping | Interbank sequence | Minothi |  | Sequence number approval by Group AML | This is an industry wide problem - Write up to Group AML on way forward . Done sent yesterday. Waiting on feedback from GAML. Group AML provide feedback. N/A. Quinton to priostise Dev with Bankserv. Ilse and LM sent the email. No mappings update and Dev requied | 19/11: Same feedback as above | 20/11/2020 Test data shared on 19/11
| Development | Development | Melissa |  |  | Pending Dev - Suspense Acc in progress, issue action date and sequence number dev. Communication sent to Quinto to prioritise with Bankserv. Project to make a decision on how to deal with this post proects | 19/11: Need to close this from a project perspective. Small issue to resolve.
| Testing | In progress | Nkateko |  |  | 80%. Waiting for suspense&impersonal to complete testing | Testing
| Defect | Testing | Minothi | In and out 85% | Suspense acc requirement /data issues | Testing -1. Address /city name also a data misalignment issue. Approval granted to use N/A as NDW confirmed it will not fail validations while we wait for DMO to fix
CMA - CPS | Requirements | Requirements N/A
| Write up (GAML/GL) | Write Up N/a
| Mapping | Mappings | Clusters/NDW |  |  | Mappings completed for exluxding non IFTR transactions, bin rage 6,7 and 2 and include China Union pay Mappings done | 19/11: There is one additional rule Melissa needs to add. - Bin number issue needs to be investigated. Nelene driving this | 20/11 2020 Melissa to investigate why the applied rulesare not working.
| Development | Development | Melissa | 2020-11-11 |  | Dev pending - for exluxding non IFTR transaction, Bin range 6,7 and 2 and include China Union to be concluded on 11/11 Dev done - Some issues on AMEX numbers that could not be linked. Suspense DEV done, Test data to go EOD. SI DEV completed test dat will be shared once Dev is online.
| Testing | Testing | Ntsoaki |  | Verifcation from source by testing team. Done | 2. Address /city name also a data misalignment issue. Reason field/ FIU. Feedback received from the FIC 16/10. Ifo not quite useful. NDW requested PM to confirm which version of the FIC schema was used to provide feedbck. SI DEV completed test dat will be shared once Dev is online Done - Testing team provided Melissa with screen shots and transaction numbers. Refreshed test data sent out - 10/11. Retest to be done.Requested data will only be prioritised after priority DEV is done.SI DEV completed test dat will be shared once Dev is online
| Defect |  | Lauretta |  | Suspense acc requirement /data issues | 2 defects to be addressed (covered under suspense and impersonal accounts). Rounding issue with account numbers (meeting with Charl to resolve). Picking up Non IFTR transactions. Source file required for retest. LM to log TRS for the Source file.Requested data will only be prioritised after priority DEV is done
CMA - Magtape | Requirements | Requirements N/A
| Write up (GAML/GL) | Not applicable
| Mapping | Address/city name not in CIS - but need to go to exceptions. |  | TBA |  | City Field issue showing N/A. Need to wait for clusters to fix. Not applicable needs to be blank will populate and go to Exceptions - to go to DMO? To check for volumes with Melissa. Volumes received and being analysed. Feedback to be given today 10/11. Exception volumes impact with this. Pending approval from business. Impacts all clusters. Session to be set up across Clusters | Risk DMO handed over/ option N/A to be used | 20/11/2020Test data shared on 19/11
| Development | In progress | Melissa |  |  | Dev pending -Suspense dev done, test data to go out by EOD 16/11.SI DEV completed test dat will be shared once Dev is online
| Testing | Include % of testing | Harry |  | 15% | Testing completed on this and waitng for the Suspense Account component.Test data to be shared today
| Defect |  |  | 2020-03-10 | Suspense acc requirement /data issues | Finalised.
Impersonal accounts | Requirements | RBB - Analysis of accounts | RBB |  |  | In progress by RBB
|  | CIB - results | Minothi |  |  | Additional data to compared to new rules. RBB - CIB accounts (close off with Phakamile)
|  | 3. Wealth - Followed up with Elena as to who will notify GAML of new impersonal accounts | Minothi |  |  | Need confirmation re notification to Group AML. Follow up on Wealth S&I accounts. Follow session with GRP AML on 12/11
| Write up (GAML/GL) | 1. An addendum to be added once the requirements are finalised | Minothi
| Mapping | 1. Mappings to be updated when the requirements are finalised | Minothi
Development
| Testing |  |  |  |  | Testing is 74% completed
| Defect | 1. Review of current defect list | Entire team
Suspense accounts | Requirements | 1. CPS, MG and ACB RBB suspense accounts to be investigated to indicate whether they would have underlying clients | Shantha |  |  | Shanta to request assistance from MC - Minothi to be included in meeting. RBB requirements rules sent 06/11 and final one senth through on 11/11
| Write up (GAML/GL) | 1. An addendum to be added once the requirements are finalised | Minothi
Mapping
| Development | Development to take place after finalisation of the mapping update | Melissa
Testing
Defect
CMA Bank Statements | Write-up | Update CMA bank statements write up | Minothi |  |  | Iniatl issue raised adressed by NDW. RBB raised additional feedback that was not raised during the review. Group PM to book a session to discuss. Issue Closed. Group PM to sent the process of how manual files will be sent to FSP by 13/11
|  | Update of methodology | Group AML
China Systems | Mapping | 1. Engaging with China Systems team to understand transactions | Tlalane |  |  | Feedback due 06/11
| Development | Development for China Systems transactions per mappings | Melissa |  |  | TL and PZ to confirm if tables are in QA
| Testing | Regression testing for completed development | TBA
Tracibility matrix | Requirements | Utilise list completed in 2019 to update | Nelene |  |  | Utilise current FIC requirements. Tlalane and Nelene busy with this. Mainly for Audit purposes
Independent testing | Bopcus | In Progress(15%) | Peter
| Non reportable |  | Peter
| Bopcard Resident | Completed | Peter
| Bopcard Non-resident |  | Peter
| CMA - ACB | Completed | Peter
| CMA - CPS | Completed | Peter
| CMA - Magtape | Completed | Peter
Product Type Code |  |  | Tlalane |  |  | Mappings to be updated and sent out 13/11
IER Status | Bopcus + Non Reportable and Bopcard Res | Inprogress | Tlalane/Nelene |  |  | Group PE to investigate Issue appears to be fixed. Looking at how to deal this going forward. Davin to follow up with BBMD team | close out
ROA exceptions - across all reporting categories | All categories | Extract to be run of all NAR clients | Nelene/melissa |  |  | 1.Provide NAR exceptions to clusters 2. Run extract for all NAR clients (deprioritised) Updated data IFTR extract received from Nelene. Davin looking into this. Nelene to facilitate bigger data set - full base to the business. MC can only prioritise this after key development is done
Exceptions management process | All categories | 1. Resolve Finsurv and CMA category financial exceptions process | Nelene | 2020-11-13 | Update write to Group AML | NS busy with documentation - Finsurv 28/10 and update a write up to Group AML Waiting for formal decision from GAML for transactional exceptions. Surekha to send out Comms Note: Nelene and Davin dealing Client data exceptions / GAML dealing Transactional data exceptions. Sudesh waiting for SARB approval to update customer ACC. | Updated write up to Grp aml
|  | 2. Resolve cluster client exceptions process | Nelene |  |  | RBB to finalise where exceptions will flow. RBB to feedback by COB 10/11
Country prefix code | All categories | Current proposed solution will not solve for the issue. Clusters to provide alternative solution | Group AML |  |  | Group AML to resolve through DMO
Solution design | All categories | IER status - IB to update current document and distribute to Group AML and Group Legal | Ilse | 2020-11-03 |  | Write up updated and sent to RBB. IER status to be reviewed with RBB for Bopcard.Meeting with NDW,Fisurv and RBB . Done
Data lineage | All categories | Confirmation of hand-over to Group AML | Lauretta | Completed |  | Email sent to stakeholders
|  | Analysis hand over to Group AML team | Lauretta | Completed |  | Completed | Done. Been handed over to Radar team
CIS/MDM migration |  | Testing of exceptions to be completed | Testing team |  |  | Cluster have requested data for this investigtion. Defects retest to confirm if issue persist after migration. Testing to share their final list with LM
GATR exceptions automation |  | Development of GATR exceptions process flow | Eric /Adaptris | 2020-10-28 | Dependent on completion of exceptions process | Adaptrisl IA received. To confirm timing today for update to the plan
Breach process |  | Not at this time | Nelene |  |  | Process has been reviewed and updated. Final review and approval once reporting categories are finalised. Nelene
Passport/ID no blank |  | Defect to be closed? | Ntsoaki | 2020-10-28 |  | ME team to review whether this is a capturing issue. NS to follow up on this. A CVH issue, not ME onboarding. RBB to follow up to close this issue. Testing team to review and close if correct results are obtained. Ntskoaki to do a retest today Closed
FIU message |  | Group AML has escalated to FIC. Awaiting feedback | Group AML | TBA | FIC | Matter raised with Group AML
Dormant accounts /GL account |  | To be resolved for RBB - escalation to Group AML required | Ilse / Group AML | 2020-11-03 |  | To be managed as part of BAU - hand over meeting 2 Nov 20 Davin dealing this with Surekha - 10/11
Approval of testing by clusters | Testing sign-off by clusters | Complete testing Complete traceability matrix Obtain sign-off | Peter / Testing team
Methodology register | Register of changes required to the methodology | First draft of registrer completed Update as an when required Provide to Group AML for update of methodology document | Lauretta / Group AML | 2020-11-03 |  | Register shared with Group AML. MJ responded that it would be updated once and requested feedback from RBB. To be managed as BAU
Financial reconciliations | 3 way recon for IFTR | Complete hand-over from James Vlok to Group Finance Complete 3 way recon and obtain approval Implement 3 way recon for IFTR | Lachelle van der Merwe / Group Finance / NDW | 2020-11-03 |  | GF - will also be BAU. Preyesh will manage this going forward. CTR first and then IFTR - round out discussion. To be managed as BAU
No | Action Items | Responsible | Feedback/Notes | Next follow up date | Status | Defect No
1 | SWIFT Inflow - Lauretta and Tlalane to engage with Mamello on this | LM/TN | 14/9/2020: 1. TN has updated mappings to include IER status and they do have it on BOPCUS for certain transactions. FINSURV team indicated that we need to include IER for BOPCUS. 2. TL and LB to engage with Mamello by COB 16/9 - LM asked to keep this item open till then 22/9/2020: 1. LM has advised that the mappings were updated and that this item should be closed | Thurs, 17th Sep | Closed
2 | SWIFT Outflow - Meeting with Mamello and FINSURV team
2.1 | SWIFT Outflow - Meeting with Mamello and FINSURV team to be held to discuss this | MC | 14/9/2020: 1. Meeting was held on 8/9 to confirm which account numbers the outgoing team would manage 2. Mamello requested dataand indicated that previous extract would suffice but she then requested Aug data - Minothi to confirm with Mamello as whether a new extract is required 16/9/2020: 1. Mamello confirmed that she wants a new extract for August so that it can be distributed to the team for them to advise on the acocunt numbers 2. See 2.3 below | Refer to 2.3 below | Open
2.2. | Meeting on 8/9: Mamello to send an email pertaining to the descriptions she requires on the exception report | Mamello | Mamello has discussed this with Melissa |  | Closed
2.3 | Meeting on 8/9: 2. Melissa to then run an extract for August 2020 to extract the outgoing FINSURV impersonal and suspense account exceptions (this would include all impersonal accounts and not be limited to the list that the incoming team provided) – the following account numbers need to be excluded as they would only be applicable to domestic transactions: 1565000218, 1565000226, 1565000234, 1565000242 The extract to include the descriptions provided by Mamello. | MC | 22/09/2020: 1. Melissa has run the extrat for the data that is available in NDW 2. Mamello has some queries pertaining to the data range as it is not for the 1st Aug - 31st Aug - Melissa has advised that the GPS data is not available in NDW for that date range 3. MC will respond to Mamello's addtional queries. |  | Open
2.4 | Meeting on 8/9: 3. Melissa to distribute the file to Mamello and the project team | MC |  |  | Open
2.5 | Meeting on 8/9: Mamello to send the file to all stakeholders and Dewald to obtain input. The team will also confirm whether we must send all the impersonal account exceptions to them or whether there is a list of accounts that is specific to the outgoing transactions team - this item will also answer Shantha's query about the MFC account number | Mamello |  |  | Open
2.6 | Mtng on 8/9:Minothi to set up meeting with Suzette Steyn and Linda Botman from Cape Town | MM | 22/09/2020: Meeting scheduled for 22/9/2020 with CT stakeholders to discuss exceptions and account numbers that the CT outgoing exceptions team will handle |  | Open
2.7 | Mtng on 8/9: Nelene to schedule a meeting with stakeholders to discuss the process after the extract has been distributed (Mamello will advise when this may be done after discussion pertaining to volumes with Dewald) | Nelene |  |  | Open
3 | Process required when a new Impersonal account is opened | Suzette/MM/Shantha | 14/9/2020: 1. CIB have given us contact details 2. Lauretta has engaged with Suzette 3. RBB still finalising I&S 16/9/2020: 1. Suzette will advise by COB Friday 2. Minothi to contact Ryan Folster to find out if there can be a process for when new impersonal accounts are opened for any cluster, can they automatically notify GAML. Also ask him whether only GBS will be allowed to open impersonal account numbers for all cluster. Ask him about suspense account numbers as well. 3. Shantha indicated he will advise who will notify GAML of whether the account needs to be considered for IFTR reporting i.e. whether funds could have been transferred to an undelrying account 22/9/2020: 1. Suzette has still not advised - LM to esclate to Elena, Ilse and Surekha 2. MM still needs to engage with Ryna | Fri, 25th Sep | Open
4 | SWIFT Transactions - issues with identifying underlying client's account number from SWIFT message
4.1 | Melissa to send Shantha examples | Melissa | Done |  | Closed
4.2 | Melissa to investigate to see if there is an issue with extra spaces that could be rectified | Melissa | 14/9/2020: Melissa to provide feedback by tomorrow 22/09/2020: 1. Melissa has invetigated and identified an issue which has been resolved and the code has been updated 2. Waiting for a rerun to test this | Mon, 28th Sep | Open
4.3 | Notify Tlalane that Bash advised that the bank's strategy is to move towards automation - She must notify the SWIFT team must work towards rectifying misplaced data on SWIFT message | Minothi | 14/9/2020: 1. MM notified TN 2. Ilse advised that it is very difficult for project to tell SWIFT team what they need to do to get their stuff automated - TN, IB need to bring this to GAML's attention as this is not a project deliverable 3. Item to be kept open until meeting with GAML is held and they take ownership to drive this change 22/09/2020: 1. To be discussed with GAML next Monday | Tues, 29th Sep | Open
5 | RBB to engage with Bradley and Jackie regarding Corporate Saver | Shantha | 14/9/2020: 1. Shantha advised that he will confirm which transactions belong to RBB and which CIB and provide feedback 2. Shantha advised that he met with Corp Saver today and that it will be carried over till next week | Mon, 21st Sep | Open
6 | Process is required when an exception is routed to the business | Nelene |  | Mon, 28th Sep | Open
7 | MFC Impersonal Account transactions
7.1 | Melissa to investigate whether she can identify MFC accounts via product code | Melissa/MM | 14/09/2020: 1. Melissa to provide feedback by COB 16/09/2020: 1. Melissa has provided feedback and Eric has provided feedback that the code is available in NDW 2. The account numbers provided were MFC CA - Minothi to confirm whether this is one of the 12 account numbers provided by the FINSURV team - if yes, FINSURV team would handle the exception and provide underlying client's details (MM still to confirm with regarding to FINSURV Outgoing team about all 12 account numbers) - covered under point 22/09/2020: 1. MM advised that the account number is not one of the 12 that the FINSURV team would be managing 2. MM has contacted Eric as CTR has a solution for identifying underlying clients for impersonal accounts - awaiting criteria from Eric | Fri, 25th Sep | Open
7.2 | Melissa to investigate GPS Out file to see if the underlying client's account number is the file | Melissa | 14/09/2020: 1. Melissa will be sending out an email to Tlalane and team as the GPS out file still contains impersonal accounts - TN and MC to meet to discuss for them to investigate 22/09/2020: 1. Melissa to chat to Tlalane pertaining to engagements with the GPS team to get their input | 1st Oct | Open
8 | Card Settlement/Project transactions
8.1 | Melissa to send Shantha CMA EFT card settlement transactions in order for him to investigate | Melissa | 14/09/2020: 1. Melissa to send one file to cover all suspense and impersonal account transactions for CMS EFT - this will cover item 12.1 2. Melissa advised that CPS and ACB completed - she just needs to engage with Shantha regarding fields he requires 16/9/2020: Shantha received the files this morning - item closed | Tues, 15th Sep | Closed
8.2 | Shantha to engage with the card team to establish which account numbers are used purely for settlement purposes | Shantha | 14/09/2020: 1. Shanta advised to not go with account numbers as there are some account numbers which are used for both settlement and have underlying clients 2. Shantha advised that he is engaging with Card to understand which account numbers are being used purely settlement purposes 3. Ilse advised that Shantha need to engage with Card to understand which card account numbers are being used purely for settlement purposes 4. MM indicated that the card team should be able to provide which settlement accounts are being used purely for settlement and those being used for dual purpose 5. Davin asked to have a focussed call to discuss this - Davin to advise who from CARD to invite and will set up the meeting | Thurs, 17th Sep | Open
9 | GBS transactions - project team to engage with GBS to understand their transactions | Phakamile | 16/09/2020: 1. MM indicated that the GBS team confirmed that it is out of scope as GBS transactions would never have underlying accounts 2. PZ investigated how to identify GBS transactions in NDW - she has referred this to another analyst within NDW 22/09/2020: 1. PZ has provided us with the table name and she will provide us with the field names of the profit code 2. MM send an email to Shantha to ask him about how to identify a transactions profit code | Wed, 23rd Sep | Open | 49
10 | CIB Corp Saver - Minothi to set up session with Shantha, Eric and Melissa to unpack further | Shantha | 16/09/2020: Shantha to have meeting and advise whether RBB and CIB will need to resolve who is owning the transactions as the transaction will be routed to them. | Fri, 18th Sep | Open
11 | Other Cluster transactions - Minothi to investigate | Minothi | 16/09/2020: 1. Wealth: MM to check account numbers against Eric's/Issack's list of impersonal account numbers 2: CIB: Melissa to advise on account category and client type 22/9/2020: 1. Harry to find original email as MM investigations show that the account numbers do belong to Wealth - confirmed against the list provided by Wealth head of finance 2. MC has advised on client type. Engaged with Eric about account category - Eric requested examples from CIB -CIB has sent through the examples. Eric invesigating in NDW . | Fri, 25th Sep | Open
12 | CMA EFT Suspense account transactions
12.1 | Melissa to send Shantha CPS, MG and ACB GL suspense account transactions | Melissa | Closed on 16/9/2020 |  | Closed
12.2 | Shantha will advise with regards to CMA EFT GL settlement transactions that being with a 9 would have an underlying clients | Shantha | 16/9/2020: Shantha advised that this is in progress | TBC | Open
13 | FINSURV Exceptions: Shantha to advise which business areas these impersonal account transactions need to be routed to | Shantha | 16/9/2020: 1. Shantha advised that this item is In progress 2. Ilse advised that the transaction exceptions would be sent via email but in future it will possibly be via.GATR (Shantha asked to confirm with Bash) | TBC | Open
14 | CMA EFT: Shantha to advise which business areas CPS, MG and ACB exceptions need to be routed to | Shantha | 16/9/2020: 1. Shantha advised that this item is In progress 2. Ilse advised that the transaction exceptions would be sent via email but in future it will possibly be via.GATR (Shantha asked to confirm with Bash) | TBC | Open
15 | List of fields on Impersonal account exceptions report
15.1 | Minothi to engage with Melissa to confirm fields on current FIC report | Minothi | 16/9/2020: 1. Minothi indicated that this is in progress 22/9/2020: 1. Melissa and MM have met and this item is in progress | Fri, 25th Sep | Open
15.2 | Minothi to send file that was agreed with the other clusters to Shantha | Minothi | 16/9/2020: 1. Minothi indicated that this is in progress | TBC | Open
15.3 | Shantha to confirm list of fields RBB require with the RBB business areas | Shantha | 16/9/2020 Shantha awaiting file from Minothi | TBC | Open

## 00
Reporting Category / Issue | Task | Outstanding task/Progress | Responsibility | Date to complete | Blockers/Escalation | Comments
| Resolution of blank comments node | Confirm MCA Swift messages | Tlalane | 2020-10-12 | Finsurv to advise whether there should be comments nodes | 1. Confirm MCA Swift messages (TN) 2. Update on the write-up for Group AML 3. Updated script to be sent to MC for review for the duplicates. Updates to mapping if indicated by NDW
| Defect | Update write-up for Group AML to review and approve | Tlalane | 2020-10-12 | None | Document sent to Group AML for review and approval
|  |  | Group AML | 2020-10-13
|  | Duplicate swift messages | Tlalane | 2020-10-13