## Slide 1
Testing Progress Report & Plan

## Slide 2: Executive Summary
Status Update as at 10/12/2020
Testing focus for the 1 week was mainy focused on China System component :
  BopCus_In/Out, Nonreportables In/Out
27% rate achieved, and below are the results for data and Manual testing
Current Test Cases 678
Key focus areas which progress has been made and can be covered
Confidence level is high on Bopcus In and Out based on the current requirements in hand.
Confidence level is low on Non Reportable Out Testing. Defects logged for China Systems.
Confidence level is low on Non Reportable In Testing. Defects logged for China Systems due to blocker where there are no transactions flowing in
Retest for Suspense & Impersonal accounts defects testing.
Areas of concern
Reason code fix/removal – Not yet delivered
There is currently no data available for NonReportable S&I flow out, no testing done, and issue has been addressed with the project team.
There is currently no Finsurve exceptions picked up for Bopcus_Out for the month of Oct, no testing done, and issue has been addressed with the project team
There is currently no transactions flowing through for NonReportable China System flow in, no testing done, and issue has been addressed with the project team.

## Slide 3: Deliverables Cont1
System | Category | Scope | Status | Comment | Risk /Issue | Mitigation | Confidence level
China Systems | NonRep_In | Yes | Blocked | Blocked, no testing conducted | There is currently no transactions flowing through for ,no testing done, and issue has been addressed with the project team |  | Lowest
China Systems | Bopcus_In | Yes | Testing currently underway but this will be tested by CIB Team |  |  |  | High
China Systems | Bopcus_Out | Yes | Test Execution | Testing in progress, Transaction comment field not populated issue Amount local on NDW data file not the same as the rand amount as the Rand value on Finsurv issues Institution name for not my client populated with Swift Code | None |  | High
China Systems | NonRep_Out | Yes | Test Execution | Testing in progress, no issues | None |  | High

## Slide 4: Deliverables Cont2
 | BopCard_Resident_In | Yes | Test Execution | Regression taking place | None |  | High
 | BopCard_Resident_Out | Yes | Test Execution | Regression taking place | None |  | High
 | BopCard_Non_Resident_In | Yes | Test Execution | Regression taking place | None |  | High
 | BopCard_Non_Resident_Out | Yes | Test Execution | Regression taking place | None |  | High

## Slide 5: Deliverables Cont2
 | BopCus_In | Yes | Test Execution | Regression underway after China System Testing |  |  | High
 | BopCus_Out | Yes | Test Execution | Regression underway after China System Testing |  |  | High
 | BopCus_In_Reversals | Yes | Test Execution | Regression underway after China System Testing |  |  | High
 | BopCus_Out_Reversals | Yes | Test Execution | Regression underway after China System Testing |  |  | High
 | NonRep_In | Yes | Test Execution | Regression underway after China System Testing |  |  | High
 | NonRep_Out | Yes | Test Execution | Suspense and Impersonal accounts not tested due to data unavailability. China System testing in progress | Unknown impact , development done, however not able to test. |  | Lowest
 | CPS_In | Yes | Test Execution | Regression taking place | None |  | High
 | CPS_Out | Yes | Test Execution | Regression taking place | None |  | High

## Slide 6: Deliverables Cont3
CPS_In_Reversals | Yes | Test Execution | Reason field/ FIU an issue |  |  | Medium
CPS_Out_Reversals | Yes | Blocked | Blocked, no testing conducted |  |  | Lowest
ACB_In | Yes | Test Execution | Regression underway after China System Testing |  |  | High
ACB_Out | Yes | Test Execution | Regression underway after China System Testing |  |  | High
ACB_In_Reversals | Yes | Test Execution | Regression underway after China System Testing |  |  | High
ACB_Out_Reversals | Yes | Test Execution | Regression underway after China System Testing |  |  | High

## Slide 7: Deliverables Cont3
Magtape_In_Reversals | Yes | Test Execution | Reason field/ FIU an issue |  |  | High
MagTape_Out_Reversals | Yes | Test Execution | Reason field/ FIU an issue |  |  | High
MagTape_In | Yes | Test Execution | Reason field/ FIU an issue |  |  | High
MagTap_Out | Yes | Test Execution | Reason field/ FIU an issue |  |  | High

## Slide 8: Data Testing Status
The table illustrates the status of integration for the respective scenarios in scope . It further details the availability of integration points.
Integration testing aligned to target state as understood today and Items not yet in place due to outstanding integration points.
100% rate achieved and below are the results
ACB IN(100%), ACB_OUT(100%), CPS OUT(100%), CPS OUT(100%), MAGTAPE IN(100%), BOPCARD RES IN(100%), BOPCARD RES OUT(100%),BOPCUS IN(100%),BOPCUS OUT(100%)
Scenarios Covered | Integrating Systems |  |  |  |  |  |  |  | 
 | ACB | ACB OUT | CPS | CPS OUT | MAGTAPE IN | BOPCARD RES IN | BOPCARD RES OUT | BOPCUS IN | BOPCUS OUT
Validations and Comparisons on fields, data content, row counts | J | J | J | J | J | J | J | J | J
 | No Defect | No Defect | No Defect | No Defect | No Defect | No Defect | No Defect | No Defect | No Defect

## Slide 9: Execution Summary
The below table and graphs depicts overall testing coverage for the China Systems and Suspense & Impersonal Component testing:
The Not Started are Items are test scenarios to be executed post Go Live
The Failed items are due to fields that were not on the report as per the requirement
Not Applicable are test scenarios are the Requirements from Mapping document but which cannot be tested at the present time as advised by the BA
‘Overall Coverage has been good due to added weekend (Overtime) hours.
Previous Reporting - New Cycle: S & I Execution
Consolidated | # | % | Coverage
Passed | 98 | 69% | 76%
Failed | 10 | 7% | 
Blocked | 0 | 0% | 
Not Started | 35 | 24% | 
Total | 143 | 100% | 
Current Reporting - New Cycle: China System Execution
Consolidated | # | % | Coverage
Passed | 176 | 26% | 27%
Failed | 4 | 1% | 
Blocked | 0 | 0% | 
Not Started | 498 | 73% | 
Total | 678 | 100% | 

## Slide 10: Defect Summary and Downtime
Top 2 Defects and Downtime for the past week. These are a priority and blockers for go live.
The following are the top 2 defects that requires priority:
315875 Financial transaction exceptions details are being reported as customer exceptions (In Analysis)
UID8263-49 GBS accounts are routed to Retail
Note:
There are currently 11 open defects of which 1 defects highlighted above requires priority.
6 are under retest. These will have to be resolved before go live.
Note:
The bar charts illustrates the planned testing hours vs actual testing time further detailing the downtime for as at 11/12.
Chart: Testing planned vs actual hours
| 44165 | 44166 | 44167 | 44168 | 44169 | 44170 | 44171 | 44172 | 44173 | 44174 | 44175 | 44176
Planned testing hours | 32 | 32 | 32 | 32 | 32 | 0 | 0 | 32 | 32 | 32 | 32 | 32
Down time experienced | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual testing time | 32 | 32 | 32 | 32 | 32 | 0 | 0 | 32 | 32 | 32 | 32 | 32