## BusinessFunction
Systems | Category | Scope | Status | Comment | Risk /Issue | Matigation | Confindance level
China System | Not confirmed | TBC | Analysis by the BA | This is curretly in Analysis Phase with no requirments finalised | unknown impact to the downstream when this is made to come online Requiements no Finalised as this is still in Analysis Development status not known | Allow the Business Analyst and DevTeam to test this componet. Project to accept the risk on quality of testing given the timeline | Lowest
| BopCard_Resident_In | Yes | Test Execution |  | Will be able to achieve this before go live |  | High
| BopCard_Resident_Out | Yes | Test Execution |  | Will be able to achieve this before go live |  | High
| BopCard_Non_Resident_In | Yes | Test Execution | The current test has a dependancy of a source file which is has not been tested end to end. | Regression testing will be limited to the function under test with a source file viewed as a new feeder to the process. This has unkhown impact and possible high cadance of defects The dependancy is on the CAMS file Regression Timeline will be a week. | Will need to minimize the volumes of transactions under test and adopt the risk based approach and sample the data under test | Medium
| BopCard_Non_Resident_Out | Yes | Test Execution | The current test has a dependancy of a source file which is has not been tested end to end. | Regression testing will be limited to the function under test with a source file viewed as a new feeder to the process. This has unkhown impact and possible high cadance of defects The dependancy is on the CAMS file Regression Timeline will be a week. | Will need to minimize the volumes of transactions under test and adopt the risk based approach and sample the data under test | Medium
| BopCard_Non_Resident_In_Reversals | Yes | Test Execution | The current test has a dependancy of a source file which is has not been tested end to end. | Regression testing will be limited to the function under test with a source file viewed as a new feeder to the process. This has unkhown impact and possible high cadance of defects The dependancy is on the CAMS file Regression Timeline will be a week. | Will need to minimize the volumes of transactions under test and adopt the risk based approach and sample the data under test | Medium
| BopCard_Non_Resident_Out_Reversals | Yes | Test Execution | The current test has a dependancy of a source file which is has not been tested end to end. | Regression testing will be limited to the function under test with a source file viewed as a new feeder to the process. This has unkhown impact and possible high cadance of defects The dependancy is on the CAMS file Regression Timeline will be a week. | Will need to minimize the volumes of transactions under test and adopt the risk based approach and sample the data under test | Medium
| BopCus_In | Yes | Test Execution |  | Will be able to achieve this before go live
| BopCus_Out | Yes | Test Execution |  | Will be able to achieve this before go live
| BopCus_In_Reversals | Yes | Test Execution
| BopCus_Out_Reversals | Yes | Test Execution
| BopCus_NonRep_In | Yes | Test Execution |  | Will be able to achieve this before go live | Will need to minimize the volumes of transactions under test and adopt the risk based approach and sample the data under test
| BopCus_NonRep_Out | Yes | Test Execution |  | Will be able to achieve this before go live | Will need to minimize the volumes of transactions under test and adopt the risk based approach and sample the data under test
| CPS_In | Yes | Test Execution |  | The impact of Suspense account may derail the full completion of this category, because the requirements have been finalised we have a dependance on the source file which has not been validated, timelines to have this has not been communicated and regression on CMA will be required. at lease a week of regression per catetogy. | Will need to minimize the volumes of transactions under test and adopt the risk based approach and sample the data under test
| CPS_Out | Yes | Test Execution |  | The impact of Suspense account may derail the full completion of this category, because the requirements have been finalised we have a dependance on the source file which has not been validated, timelines to have this has not been communicated and regression on CMA will be required. at lease a week of regression per catetogy. | Will need to minimize the volumes of transactions under test and adopt the risk based approach and sample the data under test
| CPS_In_Reversals | Yes | Test Execution
| CPS_Out_Reversals | Yes | Test Execution
| MagTape_In | Yes | Test Execution
| MagTape_In_Reversals | Yes | Test Execution
| ACB_In | Yes | Test Execution
| ACB_Out | Yes | Test Execution
| ACB_In_Reversals | Yes | Test Execution
| ACB_Out_Reversals | Yes | Test Execution
|  | Yes | Test Execution

## Downtime
EWCO R1 | 2019-08-19 | 2019-08-20 | 2019-08-21 | 2019-08-22 | 2019-08-23 | 2019-08-26 | 2019-08-27 | 2019-05-29 | 2019-05-30 | 2019-05-31 | 2019-06-03 | 2019-06-04 | 2019-06-05 | 2019-06-06 | 2019-06-07 | 2019-06-10 | 2019-06-11 | 2019-06-12 | 2019-06-13 | 2019-06-14 | Total hours
Planned testing hours | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 104
EWCO R1: Down time experienced | 0
Actual testing time | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [7 empty] | 104

## Maintainance
EWCO R1 | 2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-27 | 2019-05-28 | 2019-05-29 | 2019-05-30 | 2019-05-31 | 2019-06-03 | 2019-06-04 | 2019-06-05 | 2019-06-06 | 2019-06-07 | 2019-06-10 | 2019-06-11 | 2019-06-12 | 2019-06-13 | 2019-06-14 | Total hours
Planned testing hours | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 160
Maintaince of Scripts | [5 empty] | 5 | 3 | 5.5 | 8 | 4.8 |  | 8 | 6 | 7 | 8 | 7 | 3.3 | 4.5 | 3.5 | 2.5
Actual testing time | 8 | 8 | 8 | 8 | 8 | 3 | 5 | 2.5 | 0 | 3.2 | 8 | 0 | 2 | 1 | 0 | 1 | 4.7 | 3.5 | 4.5 | 5.5 | 83.9

## Deliverables
Deliverables | Comment | Status
Test Strategy | Complete
Setting up API Testing framework | Complete
Setting up front end Automation Framework | Complete
Scripting of API for CR2
Scripting of UI for CR2 | for current sprint, automation scripting is done in parallel with development. Scripts to be ran on 18th June to verify via Release pipe line test
Creation of Bitbucket Repo | In place
Reuse of Framework for Future CRn project | Complete
Sprinte 2.3 | 52 Scenarios identified. Out of the 52 only 15 wont be automated but will be checked manual and some have Analytics tool in place to validate the requirements. Scripts completed will be validated on the 18th June.

## Execution.
Harry | # |  | Ntsoaki | # |  |  |  | Peter | #
Passed | 0 | #DIV/0! | Passed | 0 | #DIV/0! |  |  | Passed | 0 | #DIV/0!
In Progress | 0 | #DIV/0! | Failed | 0 | #DIV/0! |  |  | Failed | 0 | #DIV/0!
Not yet executed | 0 | #DIV/0! | Blocked | 0 | #DIV/0! |  |  | Blocked | 0 | #DIV/0!
| 0 | #DIV/0! | Not yet executed | 0 | #DIV/0! |  |  | Not yet executed | 0 | #DIV/0!
Total | 0 | #DIV/0! | Total | 0 | #DIV/0! |  |  | Total | 0 | #DIV/0!
|  |  | Consolidated | # | % | Coverage
|  |  | Passed | 98 | 68.53% | 75.52%
|  |  | Failed | 10 | 6.993%
|  |  | Blocked | 0 | 0%
|  |  | Not yet executed | 34 | 23.78%
|  |  | Not Applicable | 0 | 0%
|  |  | Total | 143 | 100%
202
[10 empty] | 92 | 114
[10 empty] | 30 | 1