## Defect Tracker
| Cycle 1 |  |  | BP | Open | 1 - Critical | 1 - High | BP | Benji Engelbrecht |  |  | Nkateko Baloyi
| Cycle 2 |  |  | Captiva | Closed | 2 - High | 2 - Medium | Captiva | Deon Swanevelder |  |  | Xihluke Mabasa
| Cycle 3 |  |  | Sigver | Re-Open | 3 - Medium | 3 - low | EVRS | Maria Ranala
| Cycle 4 |  |  |  | CR Requested | 4 - Low |  | MDM | Mahlodi Baloyi
| Cycle 5 |  |  |  | Known Prod Issue |  |  | Sigver | Tanya (BBD)
| Cycle 6 |  |  |  | Moved (Next Release) |  |  |  | Dumisani Sithole
| Cycle 7 |  |  |  | Business Issue |  |  |  | Matthew George (MDM)
| Cycle 8 | [7 empty] | Sigver team
BP1902 MDM Release - Captiva - Manual Defect Tracker
[9 empty] | DEFECTS PER SPRINT: | Cycle 1 | 2
[6 empty] | DEFECTS PER STATUS: | Open | 0 |  | Cycle 2 | 4
|  |  | DEFECT OWNER: | BP | 2 |  | Closed | 10 |  | Cycle 3 | 3
|  |  |  | Captiva | 8 |  | Re-Open | 0 |  | Cycle 4 | 0
[7 empty] | CR Requested | 0 |  | Cycle 5 | 0
[7 empty] | Known Prod Issue | 0 |  | Cycle 6 | 0
[7 empty] | Moved (Next Release) | 0 |  | Cycle 7 | 0
[7 empty] | Busines Issue | 0 |  | Cycle 8 | 0
[6 empty] | Total: |  | 10
[6 empty] | SYSTEM | BP | 2
[7 empty] | Captiva | 8
|  |  | Total: |  | 10
[6 empty] | Total: |  | 10
[9 empty] | Total: |  | 9
b
[14 empty] | Open | Closed | Open | Closed | Open | Closed | Open | Closed
# | TEST CYCLE | DEFECT NUMBER | DEFECT DESCRIPTION | SYSTEM | DEFECT STATUS | SEVERITY | PRIORITY | DEFECT OWNER | ASSIGNED TO | DATE LOGGED | DATE CLOSED | TESTER | COMMENTS | Mobile - WAP | Mobile - WAP | Mobile - APP | Mobile - APP | Mobile - USSD | Mobile - USSD | Internet Banking | Internet Banking
1 | Cycle 1 | 301796 | On Captiva, there are no records that match the FICA reference EPN Impacted: 600002229390 Verification type: New/Existing with Damaged ID acting on behalf of another | Captiva | Closed | 3 - Medium | 2 - Medium | Captiva | Benji Engelbrecht | 09/05/2019 | 22/05/2019 | Nkateko Baloyi | 16/05 - Benji suggest that we move the defect to monitoring. If the issue happens again, he will investigate 22/05 As per the feedback from Benji, this could be due to a bug in BP that has been fixed since the beginning of April. Testing team is unable to replicate the issue, this will be closed.
2 | Cycle 1 | 301854 | Captiva updates the Document Status correctly but the Fica Status doesn't pull through to CIS EPN Impacted: 600002367304 Verification type: New/Existing with Green bar coded or Smart Card ID acting on behalf of another | Captiva | Closed | 2 - High | 1 - High | Captiva | Benji Engelbrecht | 10/05/2019 | 17/05/2019 | Nkateko Baloyi | 17/05 - re-tested, resolved
3 | Cycle 2 | 302629 | All the name change verification types that were processed thus far failed the FICAFlagConversion (Downgrade table) | Captiva | Closed | 3 - Medium | 2 - Medium | Captiva | Benji Engelbrecht | 17/05/2019 |  | Nkateko Baloyi
4 | Cycle 2 | 302641 | Cases that have been processed but did not update CIS. This is an existing Prod incident that must be addressed in QA Verification types impacted: New/ Existing Client CM2 + CM44 New/Existing Client CM1/CM9 | Captiva | Closed | 2 - High | 1 - High | Captiva | Benji Engelbrecht | 17/05/2019 |  | Nkateko Baloyi
5 | Cycle 2 | 302925 | Unable to add "Director" as relationship error 31 and13 pop up when adding "Director" as relationship to the client After capturing details for AP and click apply button error 31 and 13 pop up. | BP | Closed | 1 - Critical | 1 - High | BP | Tanya (BBD) | 21/05/2019 | 22/05/2019 | Xihluke Mabasa | 22/05 Please note that we do not have a Windows 10 support agreement in place. The runtime 13 is due to Windows 10. DIRECTOR on CIS is HAS EXECUTIVE DIRECTOR on MDM
6 | Cycle 2 | 302989 | FICA Verification Type not found on BP system. The following Client Verification Type are not found on BP when conducting FICA. • Associated Party with director change • Associated Party without director or address change • Associated Party without CC member changes • Associated Party where CC Converted • Associated Party without director or address change • Associated Party with Full certificate of confirmation or disclosure certificate • New/Existing Client CM4/CM3 | BP | Closed | 1 - Critical | 1 - High | Captiva | Dumisani Sithole | 21/05/2019 | 24/05/2019 | Xihluke Mabasa | 23/05 - Know Prod issues, FICAflagconversion table catered for this verification
7 | Cycle 3 | 303079 | IDM export failed after realising batch on Captiva | Captiva | Closed | 1 - Critical | 1 - High | Captiva | Benji Engelbrecht | 22/05/2019 |  | Xihluke Mabasa
8 | Cycle 3 | 303357 | ValidateClientVerificationTypeMDM RetrieveParty: No Party Exists for CIS:600002401315” | Captiva | Closed | 1 - Critical | 1 - High | Captiva | Matthew George (MDM) | 24/05/2019 |  | Xihluke Mabasa
9 |  |  | Asylum Seeker"Internal Runtime error pop-up and the lines are missing on the drop down."for FICA Create Asylum seeker and FICA the client On FICA Verification select authority change Click documentation tab to select documents Internal Runtime error pop-up and the lines are missing on the drop down. Only two(2) displayed under proof of identity instead of three(3). | Captiva | Closed | 2 - High | 1 - High | BP | Dumisani Sithole | 30/05/2019 |  | Xihluke Mabasa
10 | Cycle 3 | 604517 | Unable to Login on Captiva Unable to Login on Captiva error displayed_"Server Cannot be contacted try again later or Use another server" | Captiva | Closed | 1 - Critical | 1 - High | Captiva | Benji Engelbrecht | 04/06/2019 |  | Xihluke Mabasa
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## GATR_IFTR_Test Coverage_QA
|  |  |  | 1 | 2 | 3 | 4
|  |  |  | 1 | 2 | 3 | 4
|  |  | Category: | goAML_GATR IFTR Customer Exceptions
|  |  | Cycle : | Cycle 1 | Cycle 2 | Cycle 3 | Cycle 4 | Clean-Run | Comments
|  |  | Environment: | QA | QA | QA | QA | QA
Responsible Tester:
Requirement | # | Scenario ID | Test Scenario
goAML_GATR IFTR Customer Exceptions | 1 | TC01 | Verify that you can login to gatr with user role (Manager) | Not Started | Not Started | Not Started | Not Started | Not Started |  | goAML_GATR IFTR Customer Exceptions - Cycle 1 | [7 empty] | Lotto
| 2 | TC02 | As manager Verify that the system creates the tasks for incomplete/ incorrect client data that needs to be remediated | Not Started | Not Started | Not Started | Not Started | Not Started |  | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed | Not Applicable | Not Started | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed
| 3 | TC03 | Verify that you can login to GATR with user role (Remediation officer) | Not Started | Not Started | Not Started | Not Started | Not Started |  | 39 | 36 | 0 | 0 | 0 | 0 | 3 | In Progress | 0 | 189 | 4 | 4 | 4 | 4
| 4 | TC04 | As manager and verify that all tasks are assigned to the correct user group(RBB) | Not Started | Not Started | Not Started | Not Started | Not Started |  |  | 92.31% | 0% | 0% | 0% | 0% | 7.692% | Passed |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 5 | TC05 | As manager Verify that all the columns for customer exceptions are displayed and have data populated in each column | Not Started | Not Started | Not Started | Not Started | Not Started | [8 empty] | Failed
| 6 | TC06 | Login to GATR as manager and assign Tasks to the remediation officer | Not Started | Not Started | Not Started | Not Started | Not Started | [8 empty] | Can't Proceed
| 7 | TC07 | As Manager verify that the exception that come to your queue are unique based on the DCAR | Not Started | Not Started | Not Started | Not Started | Not Started |  | BP2004 MDM Release_Captiva - Cycle 2 | [6 empty] | N/A |  | WAP
| 8 | TC08 | As manager verify that you can perform the following actions on a task; Add comment; Take Task; Reroute task | Not Started | Not Started | Not Started | Not Started | Not Started |  | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed | Not Applicable |  |  | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed
| 9 | TC09 | As remediator verify that you can perform the following actions on a task; Add comment; Take Task; Reroute task | Not Started | Not Started | Not Started | Not Started | Not Started |  | 39 | 36 | 0 | 0 | 0 | 0 | 3 |  |  | 0 | 189 | 4 | 0 | 0 | 0
| 10 | TC10 | As manager verify that you can forward tasks to remediation officers | Not Started | Not Started | Not Started | Not Started | Not Started |  |  | 92.31% | 0% | 0% | 0% | 0% | 7.692% |  |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 11 | TC11 | As manager verify that the SLA date is based on when the task was created | Not Started | Not Started | Not Started | Not Started | Not Started
| 12 | TC12 | As manager verify that the set enterprise wide SLA time on the report type of the exception CTR is 0,1,2 = 2 working days | N/A | N/A | N/A | N/A | N/A | Not Applicable for IFTR. The scenario is only applicable to CTR | [9 empty] | APP
| 13 | TC13 | As manager verify that the set enterprise wide SLA time on the report type of the exception IFTR is 0,1,2,3, = 3 working days | Not Started | Not Started | Not Started | Not Started | Not Started |  | BP2004 MDM Release_Captiva - Cycle 3 | [8 empty] | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed
| 14 | TC14 | As manager verify that notification for new tasks is received | Not Started | Not Started | Not Started | Not Started | Not Started |  | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed | Not Applicable |  |  | 0 | 0 | 0 | 4 | 4 | 4
| 15 | TC15 | As manager verify that the assigned tasks have been assigned to the correct user | Not Started | Not Started | Not Started | Not Started | Not Started |  | 39 | 36 | 0 | 0 | 0 | 0 | 3 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 16 | TC16 | As Manager/ remediation officer Verify that as user you can view the customers data for task assigned to them but cannot edit the client data | Not Started | Not Started | Not Started | Not Started | Not Started |  |  | 92.31% | 0% | 0% | 0% | 0% | 7.692%
| 17 | TC17 | As a manager/remediation officer verify that you can reassign tasks to group AML and that the system forces you to add reason | N/A | N/A | N/A | N/A | N/A | Requirement cancelled/ descoped | [9 empty] | USSD
| 18 | TC18 | As manager/remediation officer verify that an escalation email is sent if task is about to reach SLA | Not Started | Not Started | Not Started | Not Started | Not Started | [10 empty] | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed
| 19 | TC19 | As manager (second line of defence) verify that an escalation email is sent if task is about to reach SLA, if a manager and remediator are not available to action a task | Not Started | Not Started | Not Started | Not Started | Not Started | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 20 | TC20 | As Remediation office / Manager verify that you can locate a task using the different locate options | Not Started | Not Started | Not Started | Not Started | Not Started |  | BP2004 MDM Release_Captiva - Cycle 4 | [9 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 21 | TC21 | As remediation officer verify that you can reset returned searched results | Not Started | Not Started | Not Started | Not Started | Not Started |  | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed | Not Applicable
| 22 | TC22 | As remediation officer verify that you can reset returned searched results | Not Started | Not Started | Not Started | Not Started | Not Started |  | 39 | 36 | 0 | 0 | 0 | 0 | 3 |  | TEST COVERAGE SUMARRY
| 23 | TC23 | As remediation officer verify that you can Take task from the unassigned queue | Not Started | Not Started | Not Started | Not Started | Not Started |  |  | 92.31% | 0% | 0% | 0% | 0% | 7.692%
| 24 | TC24 | As remediation officer verify that if the data has been updated on the source system an escalation is not sent for that task | Not Started | Not Started | Not Started | Not Started | Not Started | [9 empty] | RTC |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
| 25 | TC25 | As remediation officer verify that the system allows user to capture reason for missed SLA | Not Started | Not Started | Not Started | Not Started | Not Started | [9 empty] | Pre-Paid Beneficiaries |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
| 26 | TC26 | As a remediation officer verify that the system auto closes all tasks that have been validated by the system as complete | Not Started | Not Started | Not Started | Not Started | Not Started | [9 empty] | TOTAL | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
| 27 | TC27 | As remediation officer verify that if a task has been reopened an escalation email is sent to the manager and the remediation officer | Not Started | Not Started | Not Started | Not Started | Not Started
| 28 | TC28 | As remediation officer verify that based on the client ID or Co registration that the system can identify when the client has multiple CIS numbers | Not Started | Not Started | Not Started | Not Started | Not Started
| 29 | TC29 | As remediation officer verify that the system removes the indicator for source data update if data is not updated after next day’s CTR and IFTR batch run. | N/A | N/A | N/A | N/A | N/A | Requirement cancelled/ descoped.
| 30 | TC30 | As remediation officer verify that the captured client information has been updated on NDW after batch run | Not Started | Not Started | Not Started | Not Started | Not Started
| 31 | TC31 | As a remediation officer verify that clients that have not been remediated remain on the report and aging for those clients is increased by a day | Not Started | Not Started | Not Started | Not Started | Not Started
| 32 | TC32 | As a remediation officer update task on the source system but do not action/confirm task on gatr | Not Started | Not Started | Not Started | Not Started | Not Started
| 33 | TC33 | Create a client on the source system with no Dcar captured | Not Started | Not Started | Not Started | Not Started | Not Started
| 34 | TC34 | Create a client on the source system with no branch captured | Not Started | Not Started | Not Started | Not Started | Not Started
| 35 | TC35 | As Manager or remediation officer verify that you can reassign / reroute a task to another cluster | Not Started | Not Started | Not Started | Not Started | Not Started
| 36 | TC36 | Verify that the SLA date is calculated correctly even if the tasks are not generated on gatr the same day that they were created | Not Started | Not Started | Not Started | Not Started | Not Started
| 37 | TC37 | Verify that the filter criteria are set based on the task groups the user is assigned to. By default, all the relevant tasks for the user are shown | Not Started | Not Started | Not Started | Not Started | Not Started
| 38 | TC38 | Verify that the is able to distinguish Corporate Saver exceptions. | Not Started | Not Started | Not Started | Not Started | Not Started
| 39 | TC39 | Verify that the GATR system displays SLA days remaining for each exception task on the landing page | Not Started | Not Started | Not Started | Not Started | Not Started
|  |  |  | Not Started | Not Started | Not Started | Not Started | Not Started
[18 empty] | RTC | [6 empty] | WAP | [5 empty] | APP | [5 empty] | USSD
|  |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | [9 empty] | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed |  | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed
|  |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | [9 empty] | #REF! | 25 | 0 | 0 | 0 | 0 |  | #REF! | 25 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0
|  |  |  | Not Started | Not Started | Not Started | Not Started | Not Started
|  |  |  | Not Started | Not Started | Not Started | Not Started | Not Started
|  |  |  | Not Started | Not Started | Not Started | Not Started | Not Started
[18 empty] | Favourite Transactions | [6 empty] | WAP | [5 empty] | APP | [5 empty] | USSD
[18 empty] | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed |  | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed
[18 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
NEDBANK PRIVATE WEALTH
Lotto
[18 empty] | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed
[18 empty] | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
WAP
[19 empty] | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
APP
[19 empty] | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
USSD
[19 empty] | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TEST COVERAGE SUMARRY
[19 empty] | PLANNED TC | TC EXECUTED | TC PASSED | TC FAILED | % EXECUTED | % PASSED | % FAILED
[18 empty] | Lotto |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | RTC |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Pre-Paid Beneficiaries |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | TOTAL | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | RTC | [6 empty] | WAP | [5 empty] | APP | [5 empty] | USSD
[18 empty] | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed |  | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed
[18 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Pre-Paid Beneficiaries | [6 empty] | WAP | [5 empty] | APP | [5 empty] | USSD
[18 empty] | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed |  | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed
[18 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Favourite Transactions | [6 empty] | WAP | [5 empty] | APP | [5 empty] | USSD
[18 empty] | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed |  | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed | No of Test Cases | Not Started | In Progress | Can't Proceed | Passed | Failed
[18 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!